## Total geo
|  | სავარაუდო ხარჯი (USD) | დარჩენილი თანხა (USD) |  |  | 6000000 | retroactive
|  | 41500000 | 34861578
საქართველო - COVID-19-ზე რეაგირების საგანგებო ღონისძიებების პროექტი
პროგრამული კოდები | საქონელი | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი | საბიუჯეტო რესურსი | მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები | 5 ოქტომბერი | რესურსი
27 03 03 11 01 | 1. პერსონალური დაცვის საშუალებები COVID19/G/DC-05 | 5000000 | 179820 | 4820180 |  | -1186920 | 6007100 | დავაკორექტირო | 34023536.9
27 04 03 | 2. კოვიდ-19 საპასუხო ღონისძიებებში ჩართული ჰოსპიტლებისთვის აღჭურვილობის შეძენა (რუხი, ბათუმი, თბ. ინფექციური, თბ. საუნივერსიტეტო, ქუთ. რეგიონული, LG, და საჩხერის რეგ. დაწესებულებები) COVID19/G/DC-06 / | 7000000 | 403437.6 | 6596562.4 |  | -269416.368 | 6865978.768 | 0 | 30000000
27 04 03 | 3. პირველადი გადაუდებელი საპასუხო ღონისძიებებისთვის მოტოციკლები (სრული კომპლექტაცია) COVID19/G/RFQ-03 / | 1000000 | 0 | 1000000 |  | 0 | 1000000
27 04 03 | 4. ცე-ტიპის (ინტენსიური დახმარების) მობილური ჯგუფებისთვის მნქანები და აღჭურვილობა (სრული კომპლექტაცია) 30 ცალი COVID19/G/RFQ-01 / | 2250000 | 0 | 2250000 |  | 300000 | 1950000
27 03 03 11 01 | 5. სადიაგნოსტიკო მასალები COVID19/G/DC-07 / | 25250000 | 14107378.4 | 11142621.6 |  | 4176121.6 | 6966500 | რა გვაქვს ნაყიდი, ასევე გეგმა
27 04 03 | 6. სასწრაფო-გადაუდებელი დახმარების ცენტრის აღჭურვილობა COVID19/G/RFQ-02 / | 5300000 | 313476 | 4986524 |  | 1986524 | 3000000
27 04 03 | 7. ინტერნეტ-საკომუნიკაციო აღჭურვილობა / კომპიუტერული ტექნიკა საზ. ჯანდაცვის დაწესებულებებისთვის COVID19/G/RFQ-07 / | 50000 | 379240 | -329240 |  | -329240 | 0 | 20760
27 04 03 | 8. ავტოსატრანსპორტო საშუალებები მარეგულირებელი სააგენტოსათვის COVID19/G/RFQ-04 / | 350000 | 0 | 350000 |  | 350000 | 0
27 04 03 | 9. პირველადი ჯანდაცვის აღჭურვა (100 ამბულატორია) | 3000000 | 388020 | 2611980 |  | 2611980 | 0
0 | ჯამი | 49200000 | 15771372 | 33428628 |  | 7639049.232 | 25789578.768
0
0 | რეაბილიტაცია | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი |  | მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები
27 04 03 | COVID19/CW/RFB-01 / ჯანდაცის საწესებულებებისთვის სარეაბლიტაციო სამუშაოაები | 1000000 | 0 | 1000000 |  | 704628 | 295372
0 | ჯამი | 1000000 | 0 | 1000000 |  | 704628 | 295372
0
0 | საკონსულტაციო მომსახურება | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი |  | მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები
27 03 03 11 01 |  | 300000 | 6250 | 293750 |  | 293750 | 0
0 |  | 300000 | 6250 | 293750 |  | 293750 | 0
0
27 03 03 11 02 | კარანტინი, მზაობა, ქეისების მართვა | 20500000 | [6 empty] | 35137529.3
0
0 | კომპონენტი 3. პროექტის მართვა და მონიტორინგი
0 | საკონსულტაციო მომსახურება | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი |  | მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები
0 |  | 300000 | 160800 | 139200 |  | 138200 | 1000
27 03 03 11 04 | PIU თანამშრომელთა შრომის ანაზღაურება (ლარი) | 300000 | 160800 | 139200 |  | 138200 | 1000 |  | 152600
0
| ჯამი | 71300000 | 15938422 | 34861578

## საბიუჯეტო
კომპონენტი 1
პროგრამული კოდი | დასახელება | რესურსი | საკასო ხარჯი | რესურსი - WB
27 03 03 11 01 | ახალი კორონავირუსით (SARS-CoV-2) გამოწვეული ინფექციის (COVID-19) მართვის ხელშეწყობისთვის სამინისტროს მიერ განსახორციელებელი ღონისძიებები | 34023536.9 | 60074626.97 | 52508661.668
27 03 03 11 02 | ახალი კორონავირუსით (SARS-CoV-2) გამოწვეული ინფექციის (COVID-19) მართვისთვის გასატარებელი ღონისძიებები | 35137529.9 | 26385163.19 | 66215000
27 03 03 11 03 | ახალი კორონავირუსით (SARS-CoV-2) გამოწვეული ინფექციის (COVID-19) მართვის ხელშეწყობისთვის ცენტრის მიერ განსახორციელებელი ღონისძიებები | 19537359.85 | 17255359.01 | 0
27 03 03 11 04 | COVID-19-ზე რეაგირების საგანგებო ღონისძიებების მართვა (WB) | 0 |  | 152600
27 03 03 11 05 | COVID-19 ვაქცინის ხელმისაწვდომობა | 18000000 | 18000000 | 0
27 04 03 | COVID-19-ზე რეაგირების საგანგებო ღონისძიებების უზრუნველსაყოფად სამედიცინო დაწესებულებათა აღჭურვა/რეაბილიტაცია | 30000000 |  | 59644619.272
| ს უ ლ | 136698426.65 | 121715149.17 | 178520880.94
კომპონენტი 2
პროგრამული კოდი | დ ა ს ა ხ ე ლ ე ბ ა | რესურსი | საკასო ხარჯი | რესურსი - WB
27 02 06 02 01 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (სოციალურად დაუცველი ოჯახებისათვის ფულადი დახმარება/ კომპენსაცია) | 7069105 | 53193991 | 345610000
27 02 06 03 01 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (ფულადი დახმარება/კომპენსაცია დაქირავებით მომუშავე ფიზიკური პირებისათვის) | 34041800 | 106284200
27 02 06 03 02 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (ფულადი დახმარება/კომპენსაცია ინდ.მეწარმეებისა და გადასახადის გადამხდელი ფიზიკური პირებისათვის) | 5000000 | 74646800
2 | ინდ. მეწარმეებს, მცირე ბიზნესის სტატუსის მქონე მეწარმე ფიზიკურ პირებს და ფიქს.გადასახადის გადამხელ ფიზ. პირებს, რომელთაც მიმდინარე წლის პირველ კვარტალში უფიქსირდებათ ეკონომიკური აქტივობა ან/და შემოსავლები ეკონომიკური საქმიანობიდან, ასევე მიკრო ბიზნესის სტატუსი მქონე ფიზიკურ პირებს, რომელთაც ეს სტატუსი მიენიჭათ 1 აპრილა მდე და არ იღებენ დაფინანსებას ბიუჯეტიდან
2.7 | ვ) ნებისმიერ ფიზიკურ პირს, რომელიც საქართველოში გადასახადის გადამხდელად რეგისტრირებული პირისაგან (გარდა არამეწარმე ფიზ.პირებისა) წარადგენს დამადასტ.დოკუმენტს, რომ პირველ კვარტალში ეწეოდა ეკონომიკურ საქმიანობა ან/და ქონდა შემოსავალი
| ს უ ლ | 46110905 | 234124991
27 02 06 01 | ახალი კორონავირუსით გამოწვეული სოციალურ-ეკონომიკური მდგომარეობის გაუარესების გამო მოსახლეობის სოციალური დახმარება (კომუნალური გადასახადების სუბსიდირება) | 133844.21 | 172774769.77
27 02 06 02 02 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (შშმ პირებისათვის ფულადი დახმარება/კომპენსაცია) | 0 | 21516399.9
27 02 06 04 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (18 წლამდე ბავშვთა ერთჯერადი სოციალური დახმარება) | 0 | 57221600

## soci (hidden)
პროგრამული კოდი | დ ა ს ა ხ ე ლ ე ბ ა | გეგმა | ვალდებულება | რესურსი - საბიუჯეტო | გადახდა | რესურსი - WB
27 02 06 | ახალი კორონავირუსით გამოწვეული სოციალურ-ეკონომიკური მდგომარეობის გაუარესების გამო მოსახლეობის სოციალური დახმარება | 782910737 | 736665987.79 | 46244749.21 | 485638660.67
27 02 06 01 | ახალი კორონავირუსით გამოწვეული სოციალურ-ეკონომიკური მდგომარეობის გაუარესების გამო მოსახლეობის სოციალური დახმარება (კომუნალური გადასახადების სუბსიდირება) | 172910737 | 172776892.79 | 133844.21 | 172774769.77
27 02 06 02 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (მოწყვლადი ჯგუფებისათვის ფულადი დახმარება/კომპენსაცია) | 85000000 | 77930895 | 7069105 | 74710390.9
27 02 06 02 01 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (სოციალურად დაუცველი ოჯახებისათვის ფულადი დახმარება/ კომპენსაცია) | 61000000 | 53930895 | 7069105 | 53193991
სოციალურად დაუცველი ოჯახების მონაცემთა ერთიან ბაზაში რეგისტრირებული ოჯახები (სარეიტინგო ქულა მეტია 65 000-ზე და ნაკლებია 100 001-ზე ოჯახის წევრთა რაოდენობის შესაბამისად)
| ოჯახის წევრთა რაოდნეობის შესაბამისად, თითოეულ წევრზე 35 ლარი | 35 | 6 თვე
| სოციალური დახმარებაერთი წევრისგან შემდგარი ოჯახი | 70
| ორი წევრი | 90
| გ) მონაცემთა ბაზაში რეგისტრირებული 100 001-მე სარეიტინგო ქულის ოჯახები, რომელთაც ჰყავთ 3 ან 3-ზე მეტი 0-დან 16 წლის ასაკის ჩათვლით ბავშვი | 100
27 02 06 02 02 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (შშმ პირებისათვის ფულადი დახმარება/კომპენსაცია) | 24000000 | 24000000 | 0 | 21516399.9
| მკვეთრად გამოხატული შეზღუდული შესაძლებლობის მქონე პირს, ასევე შეზღუდული შესაძლებლობის მქონე ბავშვს | 100 ლარი | 6 თვე
სოციალური პაკეტის მიმღები
სახელმწიფო კომპენსაციის მიმღები
27 02 06 03 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (ფულადი დახმარება/კომპენსაცია დასაქმებულთა და თვითდასაქმებულთათვის) | 460000000 | 420958200 | 39041800 | 180931900
27 02 06 03 01 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (ფულადი დახმარება/კომპენსაცია დაქირავებით მომუშავე ფიზიკური პირებისათვის) | 367233000 | 333191200 | 34041800 | 106284200
2 | დაქირავებულს, თუ იღებდა 1 მაისამდე ხელფასს და საგანგებო მდგომარეობის დროს შეუწყდა/შეუჩერდა შრომითი ურთიერთობა დამქირავებელთან ან არ იღებს მისგან ხელფასს | 200 ლარი | 6 თვე
27 02 06 03 02 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (ფულადი დახმარება/კომპენსაცია ინდ.მეწარმეებისა და გადასახადის გადამხდელი ფიზიკური პირებისათვის) | 92767000 | 87767000 | 5000000 | 74647700
2 | ინდ. მეწარმეებს, მცირე ბიზნესის სტატუსის მქონე მეწარმე ფიზიკურ პირებს და ფიქს.გადასახადის გადამხელ ფიზ. პირებს, რომელთაც მიმდინარე წლის პირველ კვარტალში უფიქსირდებათ ეკონომიკური აქტივობა ან/და შემოსავლები ეკონომიკური საქმიანობიდან, ასევე მიკრო ბიზნესის სტატუსი მქონე ფიზიკურ პირებს, რომელთაც ეს სტატუსი მიენიჭათ 1 აპრილა მდე და არ იღებენ დაფინანსებას ბიუჯეტიდან | 300 | ერთჯერადი
2.7 | ვ) ნებისმიერ ფიზიკურ პირს, რომელიც საქართველოში გადასახადის გადამხდელად რეგისტრირებული პირისაგან (გარდა არამეწარმე ფიზ.პირებისა) წარადგენს დამადასტ.დოკუმენტს, რომ პირველ კვარტალში ეწეოდა ეკონომიკურ საქმიანობა ან/და ქონდა შემოსავალი
27 02 06 04 | ახალი კორონავირუსით (SARS-COV-2) გამოწვეული ინფექციის (COVID-19) შედეგად მიყენებული ზიანის შემსუბუქება (18 წლამდე ბავშვთა ერთჯერადი სოციალური დახმარება) | 65000000 | 65000000 | 0 | 57221600

## TOTAL
|  | Cost estimate (USD) | Outstanding amount (USD) |  | 6000000 | retroactive
| Component 1. Emergency COVID-19 Response and Component 3. Project Management and Monitoring | 41500000 | 34861578
Component 1. Emergency COVID-19 Response
| GOODS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned | 5 ოქტომბერი
1101 | 1. Procurement of Personal Protective Equipment | 5000000 | 179820 | 4820180 | -1186920 | 6007100 | დავაკორექტირო
270304 | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for dedicated COVID-19 clinics: Rukhi, Batumi, Tbilisi Infectious, Tbilisi University, Kutaisi Regional, and Sachkhere Regional | 7000000 | 403437.6 | 6596562.4 | -269416.368 | 6865978.768 | 0
270304 | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | 1000000 | 0 | 1000000 | 0 | 1000000
270304 | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | 2250000 | 0 | 2250000 | 300000 | 1950000
1101 | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | 25250000 | 14107378.4 | 11142621.6 | 4176121.6 | 6966500 | რა გვაქვს ნაყიდი, ასევე გეგმა
270304 | 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | 5300000 | 313476 | 4986524 | 1986524 | 3000000
| 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | 50000 | 379240 | -329240 | -329240 | 0 | 20760
| 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | 350000 | 0 | 350000 | 350000 | 0
270304 | 9. Equipment for Primary Care Facilities | 3000000 | 388020 | 2611980 | 2611980 | 0
| SUM | 49200000 | 15771372 | 33428628 | 7639049.232 | 25789578.768
| WORKS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
| COVID19/CW/RFB-01 / Repair works of public health facilities | 1000000 | 0 | 1000000 | 704628 | 295372
270304 | SUM | 1000000 | 0 | 1000000 | 704628 | 295372
| CONSULTANCY SERVICE | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 300000 | 6250 | 293750 | 293750 | 0
1101 |  | 300000 | 6250 | 293750 | 293750 | 0
| Quarantine, Preparedness, Cost of case | 20500000
Component 3. Project Management and Monitoring
| CONSULTANCY SERVICE Component III | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 300000 | 160800 | 139200 | 138200 | 1000
|  | 300000 | 160800 | 139200 | 138200 | 1000
| SUM | 71300000 | 15938422 | 34861578

## WORKS I
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Contractors name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CW/RFB-01 / Repair works of public health facilities |  |  |  | 1000000
1 | Kutaisi Emergency Coordination and Emergency Assistance Center |  | RFB |  | 230000 | [8 empty] | 0
2 | O.Chkhobadze Disabled and Elderly Medical Rehabilitation Clinical Center |  | RFB |  | 65372 | [8 empty] | 0
3 | Tbilisi |  | RFB | [10 empty] | 0
[5 empty] | 295372 | [8 empty] | 0

## GOODS I
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /planned | Estimated Amount (US$)/planned/ | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Amendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
2.1 | 1.COVID19/G/DC-05 Procurement of Personal Protective Equipment |  |  |  | 5000000
1 | Goggles, protective | Commander Health Supply | Direct |  |  | Commander Health Supply | Commander -001/ 10.07.2020 | China | CIP |  | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
2 | GOWN Disposable |  | Direct | 3000000 | 4500000
3 | RESPIRATOR, mask, FFP2/N95, type IIR, s.u., unvalued, nose clip |  | Direct | 230000 | 250000
4 | FACE SHIELD, clear plastic, disp. |  | Direct | 40000 | 47200
5 | Boot covers with bio protection |  | Direct | 50000 | 500
6 | Headband |  | Direct | 20000 | 400
7 | gloves |  | Direct | 4300000 | 600000 | [9 empty] | 0
8 | Mask | Sino Venture | Direct | 3000000 | 609000
TOTAL |  |  |  |  | 6007100 | [9 empty] | 179820
2.1 | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital |  |  |  | 7000000
| Second hand good (CT scanner) | LTD Ivermedi. | Direct | 1 | 103980.768 | [10 empty] | 3.6372
1 | Rukhi Republic Hospital |  |  |  | 0 | [9 empty] | 0 | 3.0782
1 | Batumi |  |  |  | 0 | [9 empty] | 0
1 | Tbilisi Infectious Disease Hospital |  |  |  | 0 | [9 empty] | 0
1 | Chkhobadze medical center in Kutaisi |  |  |  | 0 | [9 empty] | 0
1 | ICU of the Infectious LG Hospital in Kutaisi |  |  |  | 0 | [9 empty] | 0
1 | Sachkhere Hospital |  |  |  | 0 | [9 empty] | 0
| COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services |  | Direct |  | 0 | MTECH LLC | 2020-05-21 | CHINA/Mindray |  | Ammendment N1 | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
1 | ICU of the university hospital |  |  |  | 0 | [9 empty] | 0
| dializis |  |  | 36 | 576000
| AGREEMENT FOR DELIVERY OF OUTPUTS (medical equipment and supplies) | UNOPS | Direct |  | 6185998 | UNOPS | August, 2020 |  |  |  | delivery schedules of the items/supplies will be determined in consultation with the parties
TOTAL |  |  |  |  | 6865978.768 | [9 empty] | 403437.6
2.1 | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets |  | Limited |  | 1000000
| Motorcycle for ambulance first responders with helmets |  |  | 50 | 1000000 | [9 empty] | 0
TOTAL |  |  |  |  | 1000000 | [9 empty] | 0
2.1 | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) |  | Limited |  | 2250000
| Intensive Care Mobile Unit (30 Units) |  | RFQ | 30 | 1950000
TOTAL |  |  |  |  | 1950000 | [9 empty] | 0
1.1 | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies |  | Direct |  | 25250000
| Rapid COVID-19 Test Cassette |  | Direct |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Amendment N1 | Delivered | 97000 | Delivered | 5, 20 USD | 504400
|  |  | Direct |  |  |  |  | CHINA | CIP | Amendment N2 | Until August 5, 2020 | 100 000 | Delivered | 5, 20 USD | 520000
| Procurement of Standard COVID-19 Antigen Tests |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP |  | Delivered | 50000 | Delivered |  | 612200
| COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) |  | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
| Thermos Scientifics COVID-19 tests |  | Direct |  |  | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) |  | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
| Standard COVID-19 AG Test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) |  | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
| Xpert Xpress SARS-CoV-2 kit/10 tests |  | Direct |  |  | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP |  | October | 2000 packs | 2020-10-30 |  | 478240.4
| Nucleic Acid Diagnostic Kit 124 test |  | Direct |  |  | SANSURE BIOTECH INC | COVID19GDC-14 | CHINA | CIP / (NCDC) |  | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
| GeneMATRIX Viral RNA/DNA Purification Kit (100 detection |  | Direct | 125,000 (1250 Kits) |  | Bio Medi LLC | COVID19GDC-16 | EURX, Poland | CIP / (NCDC) |  | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 1000 paks |  | 298 | 356000
| COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) |  | Direct | 1 |  | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | Switzerland / CH | CIP |  |  | 1 |  |  | 493980
| Laboratory Supplies COVID19/G/RFQ-05 |  | RFQ | 200000 | 350000 | [9 empty] | 0
| EMEA Procleix SARS-CoV-2 Assay CE IVD Reagent Procleix Panther System | LUX MED LTD | Direct | 10000 | 253000 |  |  | GRIFOLS | DDP / (NCDC) |  | within 45 days |  |  |  | 0
| MATRIX Viral RNA/DNA Purification Kit | Prima medi | Direct |  |  | Prima Medi LTD | COVID19/G/DC-15/ 07/09/2020 | Germany |  |  | DDP Within one month after contract signature | 500 Packs, 125 000 extraction |  | 3 200 GEL | 1 600 000 GEL
| Tests for Cobas | Roche | Direct | 150000 | 4026000 | [9 empty] | 0
| Omni Gene oral from microbial DNA and RNA | DNA Genetic | Direct | 50000 | 337500 |  |  | DNA genotek | CIP / (NCDC) | [5 empty] | 0
| AG/AB rapid tests | Biosensor | Direct | 200000 | 2000000 | [9 empty] | 0
| ტესტ-ნაკრები Logix Smart Coronavirus disease 2019 (COVID19) kit | შპს ირისე | Direct | 100000
| ტესტ-ნაკრები Fast Track Diagnostics | შპს ირისე | Direct | 100032
| ტესტ-ნაკრები BGI | შპს ემდიესი | Direct | 100000 | [10 empty] | 0
| TaqPath™ COVID-19 CE-IVD RT-PCR Kit | შპს ეიბიემ | Direct | 100000
| extraction |  | Direct | 150000 | [10 empty] | 0
TOTAL |  |  |  |  | 6966500 | [9 empty] | 14107378.4
| 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center |  | Open - National |  | 5300000
2 | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services |  | Direct |  | 0 | MDS LTD | 2020-05-20 | Hamilton Medical AG Switzerlan | Emergency situations coordination and urgent assistance center”. | Ammendment N1 July 16, 2020 | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
| Radio systems |  |  |  | 3000000 | [9 empty] | 0
TOTAL |  |  |  |  | 3000000 | [9 empty] | 313476
| 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities |  | Open - National |  | 50000
Computers
Camera
Camera of the patient's salon
Tablets for ambulances
TOTAL |  |  |  |  | 0 | [9 empty] | 0
| 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center |  | Open - National |  | 350000
| 15 motor Motor Vehicles for Infectious Control Monitoring Center |  | RFQ |  |  | JV LLC KIA motors Georgia and LLC GI TI Motors | 30.09.2020 |  |  |  | 100 DDP | 15 Unit |  |  | 379240
TOTAL |  |  |  |  | 0 | [9 empty] | 379240
| 9. Equipment for Primary Care Facilities |  |  |  | 3000000
1 | Furniture for Primary Healthcare Facilities |  | Direct |  |  | LLC Geo + | COVID19/G/DC-22 | LLC Geo + | DDP | [5 empty] | 60000
2 | Equipment |  | Direct |  |  | Tbilisi medic |  |  |  |  | 25 days from contact signature |  |  |  | 328020
[5 empty] | 0 | [9 empty] | 388020

## CS I
|  | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Conultant name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CS/QBS-01 / Training and technical assistance to MoLSHA |  |  |  |  | 300000
1 | COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Consultant Services |  | Direct |  | 0 | [8 empty] | 3125
2 | COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Consultant Services |  | Direct |  | 0 | [8 empty] | 3125
| TOTAL |  |  |  |  | 0 | [8 empty] | 6250

## CS COMP.III
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Amount (US$)/pland/ | Conultant name | Contract N/ signed dated | Duration monthe/day | Ammendments | Delivery Date | Actual Total Price per Line item (Col. 7+8)
PIU |  |  |  | 300000
COVID19/CS/INDV-01 / Procurement Manager | Project Management |  | Direct | [6 empty] | 36000
COVID19/CS/INDV-05 / Social Standards Specialist | social specialist |  | Direct | [6 empty] | 19200
COVID19/CS/INDV-02 / Financial Manager | Financial manager |  | Direct | [6 empty] | 30000
COVID19/CS/INDV-06 / Environmental Standards Specialist | enviromental Specialist |  | Direct | [6 empty] | 19200
COVID19/CS/INDV-04 / Health Specialist | Health specialist |  | Direct | [6 empty] | 30000
COVID19/CS/INDV-03 / Procurement Specialist | Procurement specialist |  | Direct | [6 empty] | 26400
Translator | Interpreter |  | Direct | 1000
|  |  |  | 1000 | [5 empty] | 160800

## signed contracts
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
1 | Goggles, protective | Commander Health Supply | Commander -001/ 10.07.2020 | China | CIP | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
2 | COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services | MTECH LLC | 2020-05-21 | CHINA/Mindray |  | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
3 | Rapid COVID-19 Test Cassette | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Delivered | 97000 | Delivered | 5, 20 USD | 504400
|  |  |  | CHINA | CIP | Until August 5, 2020 | 100 000 | Delivered | 5, 20 USD | 520000
4 | Procurement of Standard COVID-19 Antigen Tests | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP | Delivered | 50000 | Delivered |  | 612200
5 | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
6 | Thermos Scientifics COVID-19 tests | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
7 | Standard COVID-19 AG Test | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
8 | Xpert Xpress SARS-CoV-2 kit/10 tests | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP | October | 2000 packs | 2020-10-30 |  | 478240.4
9 | Nucleic Acid Diagnostic Kit 124 test | SANSURE BIOTECH INC | COVID19GDC-14 | CHINA | CIP / (NCDC) | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
10 | GeneMATRIX Viral RNA/DNA Purification Kit (100 detection | Bio Medi LLC | COVID19GDC-16 | EURX, Poland | CIP / (NCDC) | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 1000 paks |  | 298 | 356000
11 | COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | Switzerland / CH | CIP |  | 1 |  |  | 493980
12 | MATRIX Viral RNA/DNA Purification Kit | Prima Medi LTD | COVID19/G/DC-15/ 07/09/2020 | Germany |  | DDP Within one month after contract signature | 500 Packs, 125 000 extraction |  | 3 200 GEL | 1 600 000 GEL
13 | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services | MDS LTD | 2020-05-20 | Hamilton Medical AG Switzerlan | Emergency situations coordination and urgent assistance center”. | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
14 | Furniture for Primary Healthcare Facilities | LLC Geo + | COVID19/G/DC-22 | LLC Geo + | DDP | 25 days |  |  |  | 60000
14510132