Implementation of the

Government Anti-Crisis Economic Plan

Progress Report

(March – September 2020)

The Government of Georgia

Table of Contents

Executive Summery	3

1. Introduction	6

2. General Progress	9

2.1 General Support	10

2.1.1 Support to the Citizens	10

2.1.2 Support to the Business	16

2.2 Sector Specific Support	18

2.2.1 Agriculture Sector	18

2.2.2 Tourism Sector	22

2.2.3 Construction Sector	23

2.3 Support to healthcare system	25

3. Structural Reforms	28

4. Implementation	33

4.1 Coordination Mechanism	33

4.2 Monitoring and Reporting Framework	33

4.3 Visibility and Communication	34

5. Challenges and Recommendations	36

# Executive Summery

The pandemic is having devastating effect on the world economy and like elsewhere, Georgia also suffers from its impact. Stable and sustained economic growth seen in the past 10 years, has been hit by the pandemic and restrictions of the economic activities and aggravated by the uncertainty as to how long the pandemic will last.

In order to the counter the social and economic impact of these new realities the Government of Georgia has elaborated Government’s Ant-Crisis Economic Plan (GACEP). Georgia’s Anti-Crisis policy is fully focused on the two dimensions: first and foremost to support the citizens  involving emergency assistance measures of sorts aimed at mitigating the effects of the pandemic on their daily lives. And, on the hand, supporting the business in addressing the immediate challenges that have been caused by the lockdowns and decreased economic activities associated with the measure to minimize the mobility in the country.

The report describes the activities and interventions made by the government since March 1, 2020 including September 30, 2020 regarding general support, sector specific support and support to the healthcare system (chapter 2). The report also depicts some of the outputs and results delivered by the government in some key areas of structural reforms (chapter 3).

Overall the GACEP involves 35 Activities/Interventions. These measure are distributed into the key building blocks (described in details below). During the reporting period out of the total number: 25 are still ongoing, 7 have been implemented and 3 are not yet launched. Although it is difficult at this point to properly measure impact of these measures (as much as it requires more time to properly analyze the medium-term and long-term perspectives), some insights can be already drawn.

Towards the citizen dimension the Government of Georgia, during the reporting period has implemented a number of relevant measures such as tax cuts, monthly allowances and social assistance to vulnerable groups and those left unemployed. In the framework of the GACEP the government increased pensions for the senior citizens, extended credits from the banks operating in the country, covering utility costs for households and other financial assistance measures.

During the lockdown period, in order to secure that there is no significant rise of prices on basic food, the Government of Georgia insured prices against 9 basic food products caused by exchange rate fluctuations;

The pandemic has revealed importance of the revision of the system of social assistance – leaning towards for point-awarding and financial assistance’s volume calculation. In addition, in the framework of GACEP from January 2021, pension indexation will also be introduced, meaning that the Pensions will increase at least by an amount corresponding to the inflation rate, i.e. increasing prices will not affect the actual pension;

During the reporting period, relief measures were also introduced for the business entities, particularly connected to the tourism industry, including property and income tax payment deferrals and subsidies for small hotels to cover bank loan interest expenses. The 90-day period of car customs clearance for vehicle importers has been deferred.

In addition, all legal entities were given the opportunity to restructure their loans. The Automatic VAT refund mechanism has been activated and VAT surplus refunds are expected to be doubled. To solve the liquidity problem, 600 mln GEL in long-term resources have been provided for the commercial banks. Additional 300 mln GEL have been ensured for the Credit Guarantee Schemes for the business, which is expected to secure approx. 2 billion credit portfolio State guarantee.

Beside the abovementioned horizontal activities, specific sector-based recovery plans have been developed in the areas which are of crucial importance for Georgian economy, such as agriculture, tourism and construction. These aim at supporting business actors and companies, as well as to secure job-places in the respective economic sectors.

In agriculture responding to the pandemic, the Government developed an unprecedented farmer support program within the framework of which all the components of the agricultural value chain will get financial and technical support ranging from the direct subsidies to farmers, including with the introducing new/increasing share of existing co-funding mechanisms and insurances.

Tourism, before the pandemic, used to be a rapidly growing industry with its GDP share of 11.5% and the number of the employees over 150 000. However, it suffered the most due to pandemics. Therefore, in order to help it overcome the crisis the Government developed special target measures: in 2020, the tourism businesses (Guest Accommodation Segment, Food and Beverages, Travel Agencies and Guides) are released from the property tax, while the income tax is postponed until the end of the year. The government has also ensured funds for subsidization of the loans interests payment, involving them in credit-guarantee programs and subsidization of the bank guarantees.

Construction – the third largest employer  - is a rapidly growing economic sector, with its 9% direct and indirect GDP share and the number of the employed of over 120 000 people (2019). Also, the construction industry crosses over with the other economic sectors. Therefore, continuation of its proper function is crucially important and during the reporting period the government launched number of initiatives in that direction: including introduction of subsidies of interest rate under the mortgage contract, the State guarantee of the mortgage credit portfolio for mortgage loans, bulk purchases of real estate by the state and  launching of the State guarantee scheme for completion of a residential property project.

Despite these measures and the support provided by the development partners, there are still gaps for the outstanding needs caused by pandemic. According to the IMF estimations Georgian economy is expected to shrink by 4% in 2020. Therefore, in medium and long-term perspective the country will require schemes for financing for the recovery phase. Furthermore, incentives need to be considered for capturing new investment and market opportunities arisen from COVID-19 related global re-positioning of industries and long-term policy for competitiveness.

# 1. Introduction

The pandemic, caused by the Covid-19 virus, has changed the world. The coronavirus pandemic has dealt a devastating blow to the world economy: industries, such as tourism, trade etc., have shrunk significantly. The shock affected both demand and supply. According to IMF’s basic scenario, the global economy in 2020 will drop by 3%, while in case of the worst-case scenario, a 5% decrease is anticipated. Notably, the economic crisis/shock caused by the pandemic differs remarkably from previous economic crises caused largely by an economic factor or a shock in an individual economic sector. Accordingly, in this particular case, states give top priority to the protection of human lives and health.

Before the pandemic, GDP per capita in Georgia has been increasing with average annual growth rate of 4.1% in GEL (2015 base year). Notwithstanding the challenges in the region and economic difficulties in the main trading partner countries the country managed to sustain the stable economic growth with GDP real growth rate of 5.1% in 2019 - GDP per capita reaching nominal USD 4,763. Thus, Georgia was moved from lower to upper middle-income countries by the World Bank classification.

Figure 1 GDP Per Capita Growth Rate of Georgia

Despite challenges due to depreciation of national currency, Georgian fiscal and monetary institutions managed to sustain macroeconomic stability with average annual inflation close to the targeted 3%, since 2015. Furthermore, the country managed to keep the stable budget deficit within the 3%.

Namely, in 2019, there was an unanticipated high economic growth of 5.1%. Tourism revenues amounted to 3.3 billion USD (18.4% of GDP), export revenues to 3.8 billion USD (21.2% of GDP), and net remittances to 15 billion USD (8.4% of GDP). Consequently, the national current account deficit hit the historical minimum: 5.1% of GDP. The unexpected economic growth and improved export resulted in greater budget incomes to allow the state capital investments to hit a record 8% of GDP.

However, as elsewhere, the pandemic has influenced significantly Georgia’s economic growth. This has already been reflected in sharp decline in tourism revenues, as well as Georgian export and remittances - all constituting important parts of Georgian economy and internal demand. The global lockdown is expected to shrink the world economic (4% estimates by the IMF) more than in the 2008-2009 recession.

Figure 2. Economic Growth Forecast - IMF

The pandemic has affected both the private sector and individuals, which called for finding extra resources for their direct support, as well as for the prevention of the pandemic and treatment of patients. The uncertainty as to how long the pandemic will last aggravates the economic situation. Therefore, budget reserves have been created to ensure against problems related to financing budget costs in the most pessimistic, worst-case scenario.

In addressing these challenges, the Georgian Government’s decisions have been directed toward containment of the spread of the virus on the one hand, and toward mitigating the negative impact of the virus and, to that end, supporting the private sector and citizens.  Therefore, striking a balance between protecting human lives and health and reducing the negative economic impact has been key.

It is on these two key pillar that the Government Anti-Crisis Economic Plan (GACEP) is based on. Meeting the needs of as many people and businesses as possible with limited resources are the key in order to reach out to a maximally possible number of those affected by the pandemic.

As the situation has affected many citizens and companies, the Government of Georgia developed the anti-crisis package maximally targeting said challenges, with relevant measures implemented in 2 stages.

In addition, as the situation unfolded the government of Georgia also designed so-called horizontal measures, plans for the recovery of agriculture, tourism, and construction—involving significant Governmental support to companies operating in the industries.

This progress report aims at providing interim assessment of the activities implemented by the Government of Georgia in the framework of the GACEP and depict the progress in the process of the achievement of the set targets.

The report describes the activities and interventions made by the government since March 1, 2020 including September 30, 2020 regarding general support, sector specific support and support to the healthcare system (chapter 2). The report also depicts some of the outputs and results delivered by the government in some key areas of structural reforms (chapter 3).

From the methodological point of view, it is important to mention that the report is developed based on the updated Policy Planning and Coordination System regulatory and methodological documents, which also establishes reporting standards of policy documents (i.e. Strategies, Action Plans, Concept documents).

# 2. General Progress

Overall the GACEP involves 35 Activities/Interventions. These measure are distributed into the key building blocks (described in details below). During the reporting period out of the total number: 25 are still ongoing, 7 have been implemented and 3 are not yet launched. Although it is difficult at this point to properly measure impact of these measures (as much as it requires more time to properly analyze the medium-term and long-term perspectives) some insights can be already drawn.

From structural point, the Anti-Crisis Economic Plan of the Government of Georgia is designed around three principle building blocks:

- Types of Support

- Target Groups

- Stages of Intervention.

The very design of the GACEP ensures that the each intervention of the government is very specific, targeted those who need it most and done in the most appropriate time. Such design enables the government to have a very flexibly and at the same time evidence-based approach in addressing the vulnerabilities associated with the pandemic.

Types of Support

The GACEP involves activities that are of general in their nature and as well as to the interventions in the specific economic areas which are crucial for the well-functioning of its economy as well as support that has been made for the advancements of the healthcare system. In particular, there are General Support activities (horizontal approach), Sector-Specific Support Activities and measures to support the healthcare system (Although the measure under this bulk are not included in the GACEP and thus not calculated in the Implementation rate). Under the sector-specific support, three economic sectors are identified:

- Tourism

- Agriculture

- Construction

Target Groups

Under this block the GACEP identifies groups that require special and targeted interventions. On the one hand, this includes citizens and respective vulnerable groups and bossiness, as the key drivers of the economy, on the other hand.

Stages of Intervention

As the situation has affected many citizens and companies, the Government of Georgia developed the anti-crisis package maximally targeting said challenges, with relevant measures implemented in 2 stages.

- The 1st stage, involved emergency assistance, started in March, prior to the state of emergency, and

- The 2nd stage started in April to involve broader activities.

Structure of this report is based on these three categories and the implemented activities are described in the respective sub-chapters.

## 2.1 General Support

Under the first component the GACEP the Government Anti-Crisis Economic Plan includes so called horizontal measure, that by nature targeted all physical persons and legal entities in the country that have been effected by the pandemic.

### 2.1.1 Support to the Citizens

The pandemic has effected all citizens both in economic and social terms. However, the most vulnerable groups have been effected the most. For this reason general support measures have been targeted to needs of the citizens.

However, the Covid-19 pandemic has shown significant shortfalls in provisioning suitable social services to the most vulnerable groups of the country. Therefore, the Government of Georgia considers of assessment and revision of the national social protection system that would also include not only central level, but also social assistance programmes provided at the local level. Special emphasis will be put on the People with Disabilities. The country is now in the process of elaboration of the housing policy document and its action plan in order to put forward unified vision and strategy, which would serve as a basis for handling of the problem.

LIST OF MEASURES:

1. Subsidizing utility bills for households during the lockdown (March, April, May, 2020)

Budget – 172 000 000 GEL

Status - Implemented

Progress as of September 30, 2020

3 months’ utility bills were funded for subscribers whose monthly consumption of power was less than 200 kW and that of the natural gas below 200m3 . The funding included waste management and water supply. As result:

- 1 100 000 electricity subscribers have benefited from the scheme

- 900 000 natural gas subscribers have benefited from the scheme

- Budget spent – 172 900 000 GEL

2. Subsidizing utility bills for households – 2nd stage

Budget – 280 000 000 GEL

Status - Not launched yet

Progress as of September 30, 2020

All households that consume 200kW or less per month will be provided with the reimbursements for electricity bills by the state in November, December 20202 and January, and February 2021.

3. The state support for individuals who have lost their jobs

Budget – 450 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The state initiated the support to the citizens who lost their salaries due to the economic crisis induced by the spread of the virus (those who were officially employed) and were left without any income (1200 GEL total - 200 GEL for 6 months - May-October). As a result:

- On average 100.0 thousand employees (up to 160 thousand unique employees over the program period) have benefited from the program;

- The total cost of 106 000 000 GEL as of end-September.

- Total estimated cost for 6 months 126 000 000 GEL.

4. The support to the companies to retain their employees

Budget – 250 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The state initiated the support to the companies who retained their employee and received a partial income tax exemption for the salaries of each of the employees they retained. In particular, the first 750 GEL exemption for 6 months (fully exempted) for employees with a salary of up to 1,500 GEL (May-October). As a result:

- The measure was used for around 411 500 000 thousand employees

- With the total cost of GEL216 million as of end- September.

- Total estimated cost for six months GEL255 million.

5. Support for the self-employed (those employed in the informal sectors):

Budget – 75 000 000 GEL

Status - Implemented

Progress as of September 30, 2020

The state assisted self-employed persons with a total of 300 GEL, issued in a duration of 3 months. For the identification of these citizens any pertinent information provided by the citizens that proved their income before the pandemic was used. Namely, bank statement, confirmation from the market organizer,  confirmation from the microbus route line organizer, etc. As a result:

- The measure was used by around 248 282 beneficiaries;

- With the total cost of 74 484 600 GEL.

6. Support to the vulnerable families

Budget – 50 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The government launched targeted social assistance to such families with 65,000 to 100,000 rating points for 6 months (May-October) in accordance with the number of family members, at an average of 150 GEL per family. As a result:

- Around 216 868 persons benefited and

- 76 000 families have benefited from the program,

- With the total cost of 41 000 000 GEL as of end-September.

- Total estimated cost for six months 50 000 000 GEL.

7. Support to the most vulnerable large families with

Budget – 13 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The state launched additional social assistance scheme for socially vulnerable familied with a social rating score from 0 to 100,000 and with three or more children younger than 16 received 100 GEL per month (for six-month period). As a result:

- Around 151 902 persons (24 655 households) are benefiting from the program,

- With the total cost of 11 400 000 GEL as of end-September.

- Total estimated cost for six months 14 000 000 GEL.

8. Support to the Persons with disabilities

Budget – 25 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The government made available targeted social assistance for the Persons with severe disabilities and children with disabilities by distributing 600 GEL of monetary support, 150 GEL per month (i.e. for six month period. As a result:

- Around 42 thousand people are benefiting from the program,

- With the total cost of GEL21.5 million as of end-September.

- Total estimated cost for six months GEL25 million.

9. Price Insurance for the 9 basic food products:

Budget – 14 000 000 GEL

Status - Implemented

Progress as of September 30, 2020

The Government of Georgia insured prices against 9 basic food products caused by exchange rate fluctuations to secure that there is no significant rise: in order to mitigate the devaluation effects of the national currency, a program was developed that proved to be conducive to the stability of prices on staple food products at the 1st stage of the crisis when inflation risks increased significantly. On certain conditions, the State subsidized currency exchange difference for importer companies purchasing 9 basic food products from March 15 through May 15. Consequently:

- Supplies of basic food products were secured in the country and, despite the situation in the regions, food provision in Georgia carried on without delays.

- Under the grain subsidy program, additional supplies were ensured in the country.

- The market was protected from speculative price growth.

10. Support to the children

Budget – 170 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The government implemented one-time assistance Programme for all children up to he age of 17 - providing each of with them 200 GEL. As a result:

- Around 855 000 children benefited from the program

- With actual cost of 176 500 000 GEL as of end-September

- Estimated total cost of 180 000 000 million.

11. Support to the students

Budget – 40 000 000 GEL

Status - Not Yet Launched

Progress as of September 30, 2020

The government designed Programme for Socially vulnerable students with a rating up to 150,000 points will be funded by the state for half a year of tuition fees - 1125 GEL; Socially vulnerable students with a rating below 150,000 points whose status has been suspended due to non-payment will be funded by the state with a whole year tuition fee. Due to the ongoing student registration procedures the final list of the beneficiaries are being now collected and first disbursement will be made by end of October. As a result:

- Around 17 000 students will benefit from the programme

12. Pensions Indexation System

Budget – based on the then year economic stats

Status - Not launched yet

Progress as of September 30, 2020

The government has already approved pension indexation system. From January 2021, pension indexation will also be introduced, which as result:

- will increase pensions at least by an amount corresponding to the inflation rate, i.e. increasing prices will not affect the actual pension;

- For pensioners aged 70 and over, 80% of the actual economic growth will be added to the inflation rate, i.e. the annual pension increase will surpass the inflation rate;

- Regardless of the inflation and economic growth, pensions will increase by at least 20 GEL and 25 GEL for pensioners aged 70 and over 70, respectively.

13. Credit Repayment Deferral

Budget – Commercial Banks

Status - Implemented

Progress as of September 30, 2020

In order to avoid repayment problems and penalties, Citizens, by support of the government  were given a 3 month credit repayment deferral from the commercial banks and all personal loan repayments were deferred by 3 months. As a result:

- Approx. 600 000 debtors benefited from the deferral

### 2.1.2 Support to the Business

All private sector organizations, no matter the area of their operations, have been effected by the pandemic. Therefore, the government has designed emergency and medium-term interventions for them as well:

LIST OF MEASURES:

1. Income and Property tax deferral

Budget  - 171 000 000 GEL

Status - ongoing

Progress as of September 30, 2020

Property and Income taxes of the companies were deferred until December 1, 2020. In the case of tourism industry property tax has been canceled (described below). As a result:

- Said taxes have already been deferred for more than 6000 companies.

2. Automatic VAT Return system

Budget – 600 000 000 GEL (calculated at the lunch of the Programme)

Status - ongoing

Progress as of September 30, 2020

Automatic VAT return was be enacted and VAT surplus will double creating additional liquidity for the private sector organizations. As a result:

- End-September actual VAT tax refund amounts to 630 000 000 GEL.

- It is anticipated that VAT Tax Refund will be more than 1 000 000 000 GEL.

3. Loan-guarantee scheme for the SME sector

Budget – 330 000 000 GEL

Status - ongoing

Progress as of September 30, 2020

This Programme is designed as a counter-cycle tool for bettering access to financial resources and improved liquidity management, also ensuring adequate risk distribution between the State, commercial banks and borrowers in crisis, in light of banks’ reduced tolerance toward risk. This collateral scheme is mainly designed for easier access to financial resources by small and medium-sized businesses in terms of

restructuring their previous loans or taking out new ones, including funding for floating assets. The scheme ensures Individual loan guarantee - at 80% / Bank loan portfolio guarantee – at 35%.

Within the frameworks of the program, industries directly affected by the crisis, which have potential for a relatively rapid resumption of operation in the medium-term perspective, are funded. As a result:

- 72 beneficiaries made use of credit guarantee scheme

- 16.2 Mln GEL was transferred by Enterprice Georgia for guarantees

- It is estimated that the measure will secure approx. 2 billion credit portfolio State guarantee.

4. Long-term funds available for the commercial banks

Budget – 600 000 000 GEL

Status - implemented

Progress as of September 30, 2020

The treasury of the Ministry of Finance provided the placement of an additional 600 000 000 GEL, through which the funds attracted are now placed on long-term deposits. The measure solved the emergency liquidity problem for the commercial banks.

5. Customs Clearance term for imported cars

Budget – 50 000 000 GEL

Status - Implemented

Progress as of September 30, 2020

Because of the lockdown car importers have faced significant problems in selling the car. In order to provide them relief, 90-day customs clearance term for imported cars was extended to September 1. As a result:

- 38 000 importers have benefited

6. Credit Repayment restructuring

Budget – Commercial Banks

Status - Implemented

Progress as of September 30, 2020

The government has liaised with the commercial banks to offer simplified loan restructuring for the legal entities with difficulties servicing loans. As a result:

- 7 000 legal entities used the opportunity

## 2.2 Sector Specific Support

Beside the above-mentioned general support the government has designed interventions sector-specific measure for the economic areas which are crucial for the proper functioning of the Georgian economy - providing both jobs on the market and ensuring the social security. The three key areas, based on the existing structure of the economy, are targeted under this building block:

- Agriculture

- Tourism

- Construction

### 2.2.1 Agriculture Sector

Agriculture is by far the largest employer in Georgia. Therefore its resilience and sustainability is very important for the Georgian economy. On the other hand this sector also has its implication on social aspects of the country. Namely food products produce by the agriculture sector is crucial for the ensuring that the prices on basic products are not rising and the most vulnerable groups do not fall into hunger and malnourishment.

To address immediate challenges the Interagency Coordination Council led by the Prime Minister put the Ministry of Environmental Protection and Agriculture in charge of food supply management and logistics and transport supervision. An emergency command center was created at the Ministry of Environmental Protection and Agriculture, main food products were defined to be monitored on a daily basis—in particular, import indicators, available supplies in the country, and prices were monitored—to prevent illicit behavior and to ensure the population’s social protection.

Responding to the pandemic, the Government developed an unprecedented farmer support program within the framework of which all the components of the agricultural value chain will get financial and technical support ranging from the direct subsidies to farmers, including with the introducing new/increasing share of existing co-funding mechanisms and insurances.

LIST OF MEASURES:

1. Assistance to smallholder farmers

Budget – 37 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

During the reporting period the government enacted subsidizing schemes on the agricultural goods and plowing services for registered landowners from 0.25 hectares to 10 hectares. This includes farmers to purchase fertilizers, pesticides and herbicides, seeds and seedlings and pay for tillage. As result:

- 165 000 farmers have benefited from the schemes

- 28 900 000 GEL spent

2. Diesel fuel at a preferential price to agricultural landowners

Budget – 40 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

- More than 122,000 farmers have purchased

- More than 32,000 tons of agro-diesel and

- Saved 4 300 000 GEL

3. Subsidies for Agro-insurance;

Budget – 9 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The term of the agricultural insurance program has been prolonged up to 3 years. Therefore, in case of insurance of the perennial plants, the farmers would be able to ensure their harvest for 3 calendar years. The insurance policy covers the risks, such as hail, floods, hurricane, and autumn frost. As a result during the reporting period:

- 8366 farmers have benefited from the programme

- More than 17 000 insurance cases;

- 18 000 ha land insured (32% increase against last year the same period)

- Income generated from the insured products exceed to 186 000 000 GEL

- Amount of subsidy spent 8 200 000 GEL

4. Modernization and market access of the dairy farming sector

Budget – 42 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The State “Dairy Industry Upgrading and Market Access” program was launched. The initiative aims at the diversified and sustainable dairy industry by way of upgrading the equipment and infrastructure. The program also aims at stimulating small dairies, introduction of the international standards and practice; the dairy farms are co-funded by 40-80%, i.e. 8000 GEL-195 000

- Number of beneficiaries -  255 farmers

- Amount of subsidy – 12 400 000 GEL

5. Extended Prefential Agro-credit Programme

Budget – 74 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

Loans of 5000-100 000 GEL have been issued for crop farming floating assets and the State fully subsidizes the 6 month interest rate of the secured credits, while that of the unsecured credits are subsidized by the annual 17%. It is likely to stimulate farmers to cultivate land and grow the annual crops.

- Number of beneficiaries -  255 farmers

- Amount of subsidy – 12 400 000 GEL

6. Agrarian enterprises promotion program

Budget – 10 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

For the purpose of support to the primary production, the “Agricultural Production Incentive” program was launched envisaging co-funding the purchase of the agricultural equipment and acquisition/installation of the annual crop irrigation system, as well as purchase of the fixed assets required for setting up/upgrading/expanding the hothouse facilities is going to be resumed. As a result:

- Number of beneficiaries -  387 farmers

- Amount of subsidy – 9,6 million GEL.

7. Cancellation of reclamation service prices

Budget – 13 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The farmers’ debts of 8 M GEL caused by failed payment for the land improvement service in 2012-2019, are being written off. As a result:

- 33 325 individuals and legal entities will be fully written off the obligations for land reclamation services

8. Promoting the production increase in quality Georgian agro products:

Budget – 1 500 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The government introduced a technical support program for the beneficiaries of the State-run agricultural programmes. The program is targeting at the increased national agricultural potential. The program beneficiaries are getting co-funding in terms of the introduction of international food safety management system/standards and branding. As a result, in 2020

- 16 contracts have been signed

- Funding is over 122 000 GEL

### 2.2.2 Tourism Sector

Before the pandemic, tourism used to be a rapidly growing industry with its GDP share of 11.5% and the number of the employees over 150 000 (Data from 2019). Tourism sector suffered the most due to pandemics. Therefore, in order to help it overcome the crisis and restart operation, the Government developed special target measures.

LIST OF MEASURES:

1. Abolition of property tax for the tourism industry in 2020

Budget - 45 000 000 GEL (included in the total sum of tax cuts from the general support activities for business – described above)

Status - Ongoing

Progress as of September 30, 2020

In 2020, the tourism businesses are released from the property tax. As a result business operators in the Guest Accommodation Segment, Food and Beverages, Travel Agencies and Guides have additional contingency reserves. As a result

- Around 3000 companies benefit from the tax exemption

2. Exemption and deferral of income tax for the tourism industry (included in the total sum of tax cuts from the general support activities for business – described above)

Budget - 90 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

- Approximately 3000 companies have from Guest Accommodation Segment, Food and Beverages, as well as Travel Agencies and Guides have made use of the scheme

3. Hotel loan subsidy

Budget - 60 000 000 GEL (already reflected in calculations)

Status - Ongoing

Progress as of September 30, 2020

The government initiated scheme for Subsidizing interest rate for loans of small hotels: Hotels with annual turnover below 20 million GEL received co-financing of 12 months bank loan interests. As a result:

- 1295 beneficiaries have made use of this scheme

- 16.3 mln Gel transferred by Enterprise Georgia

4. Support for travel companies and guides

Budget - 5 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The Government has initiated special Programme with measures to put the guides etc. tourism services back on track. The Government of Georgia co-funds their participation in the tourism expos and other promotional activities. The exact number of beneficiaries and amount spent is not yet available.

### 2.2.3 Construction Sector

The construction industry is a rapidly growing economic sector, with its 9% direct and indirect GDP share and the number of the employed of over 120 000 people (2019). Also, the construction industry crosses over with the other economic sectors. The loan portfolio of the industry amounts to 1.2 bn GEL and that of the bank loans secured with the residential property is approx. 5 bn GEL. As to its total credit and mortgage loan portfolio, it makes up 9.2bn GEL (18% of GDP).

The pandemic-caused economic slowdown and deteriorated economic growth targets resulted in significant reduction of advance sales due to customers’ smaller purchasing power; completion of construction projects faced a risk and accessibility to the capital worsened too because of smaller sales and bigger credit risks. The real property price fluctuations risks are bigger now. All these may significantly deteriorate the bank credit portfolio quality, which, due to its volume is hazardous to the financial sector.

Therefore, jointly with the National Bank and private sector, the Georgian Government developed the construction industry support measures to stimulate demand for residential real property and also, ensure availability of finances in the crisis.

LIST OF MEASURES:

1. Subsidization of interest on the mortgage loans

Budget - 70 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

In order to promote the demand in the sector, the government launched subsidization not over 4% of the nominal interest rate under the mortgage contract – it is believed that the State subsidy will diminish pro rata the refinancing rate. Subsidizing will continue for 5 years upon execution of the contract and may terminate in case of smaller than 5% of the refinancing rate. As result:

- 3823 beneficiaries have made use of the Programme;

- Around 100 000 GEL is already disbursed and according to schedule of loan payments around 16 000 000 GEL will be payed by the end of 2020; Payments under interest rate subsides is made according to loan payment schedules of beneficiaries, therefor full portfolio payments are expected to start from fourth quarter 2020

2. State Guarantees on Mortgage Loans

Budget - 4 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

Again to promote demand the government introduced the credit default guarantee which is set at 20% of the volume of the credit and will be effective for the term of 5 years. The guarantee applies to the loans where the borrower’s participation is not less than 10%. Incidentally, in case of the sale of the collateral of the default credit, the commercial Bank’s claim towards the creditor, natural person, will be satisfied. As a result:

- 799 beneficiaries utilized the programme;

- 3 300 000 GEL has been spent

3. Bulk purchase of the real property by the state

Budget - 150 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The State increases the bulk purchase of the residential real property worth through auctions in the framework of providing accommodation to IDPs in the country. The concrete details of the Programme are being now in the finalization process.

4. The state guarantee scheme for the completion of ongoing constructions;

Budget - 200 000 000 GEL

Status - Ongoing

Progress as of September 30, 2020

The government launched state guarantee scheme on completion of real property projects in order to ensure that the market functions properly

Call on the first lot of insurance amount (100 mln GEL) has been announced and applications deadline is on 19th of October, after which we will have exact number of issued insurance. As well insurance of ongoing constructions is based on Put Option principle and therefore it is not fully direct costs from the budget.

## 2.3 Support to healthcare system

Since spread of the virus the government of Georgia has initiated number of the programmes aimed at the strengthening of the healthcare system in Georgia. Particularly, based on the assessment of the situation as well as the available resources, in order to effectively manage the spread of the virus and make medical services available for citizens, three objectives have been identified:

- To ensure that Personal Protective Equipments (PPE) are available for the medical institutions;

- To make the testing available for the everyone based on the needs;

- To ensure that the medical institutions have enough capacity to manage the patients infected with the Covid-19

Overall, as of the October 14, 2020:

- more than 81 500 000 GEL has been spent towards these directions

- 14,440 Patients have been/are being treated

- 754,286 PCR test have been taken

LIST OF MEASURES:

1. Purchase of the Personal Protective Equipment (PPE)

Status – Ongoing

Progress as of October 14, 2020

In order to the ensure that the medical personnel have enough personal protective equipment, the Government of Georgia makes procurement for that purpose based on the needs and supplies that are available for the use. As a result:

- Around 22 350 000 GEL has been spent

- PPEs have been made available for the medical personnel without any delays and problems

2. Procurement of the testing equipment and materials

Status – Ongoing

Progress as of October 14, 2020

To ensure sufficient amount of testing is the key to success in the strategy of containment of the spread of the coronavirus. For that purpose the Government of Georgia ensured that the laboratories are equipped with enough test processing machines, as well as the required materials. This enabled the government to introduce mass testing in high risk areas and thus, prevent the exponential spread of the infection. As a result:

- Around 54 572 000 GEL has been spent

- Laboratories equipped and mass testing have been made available

3. Purchase of the medical equipment for the medical institutions

Status – ongoing

Progress as of October 14, 2020

In order to ensure that adequate medical services are available for the patients, the government of Georgian initiated mass procurement of the some medical equipment that are necessary for the proper management of the covid-19 infected patients. As a result:

- 4 650 000 GEL has been spent

- Medical institutions have been provided with the equipment for treating the Covid-19-infected patients

# 3. Structural Reforms

Despite the challenges that the world is facing, Georgian government is still pursuing its reform agenda. Even during the pandemic and lockdown period the public sector has ensured that the structural measures that have been undergoing before are not effected by the pandemic.

During the reporting period important steps have made in the areas identified in the GACEP. In particular:

Energy Sector Reform

By adopting the law on Energy and Water Supply on December 2019, the legal basis has been established for starting Energy sector reforms to develop transparent market based  relations in the sector in accordance to the requirements of relevant EU directives/regulations and commitments of Georgia taken by association agreement and accession protocol to the Energy Community treaty. Now the government of Georgia is in the process of approval and implementation of secondary legislation. According to the requirements of the law during the period of March-September 2020:

- Electricity market concept document design has been developed based on consultations with the energy community secretariat and was approved by the governmental resolution N246 on April 16, 2020;

- Based  on the above mentioned concept document, new electricity market rules have been adopted by regulatory commission resolution N46 of August 11, 2020;

- Georgian Energy Exchange that was created at the end of 2019 started training and testing of electricity day ahead market platform with participation of relevant stakeholders. Launch of the platform is planned from July 1, 2021;

- Certification rules of Transmission System Operator were adopted by the regulatory commission resolution N9 of march 27, 2020.

- Unbundling plan of electricity transmission system operator was developed, agreed with energy community secretariat and submitted by the regulatory commission to the government for approval;

- Unbundling plans by relevant DSOs  were submitted to the regulatory commission for consideration;

- First draft of gas market concept document has been developed in consultations with the energy community secretariat.

- Security of electricity supply rules are already prepared and will soon be approved by the Minister of Economy and Sustainable Development of Georgia

Energy Efficiency Reform

Despite the pandemic, the government of Georgia still continues promotion of energy savings and energy efficiency in the energy market. During the reporting period:

•	The laws on Energy Efficiency and Energy Efficiency of Buildings were adopted. Now, the GoG is in process of approval and implementation of secondary legislation according to the requirements of these laws.

•	Currently the minimal energy efficiency requirements of the buildings are being prepared and soon will be submitted to the government for approval.

•	In parallel, the Ministry of Economy and Sustainable development started coordination process of all public bodies to meet the requirements of the law about renovation of at least one percent of public buildings per year  to meet the minimal energy efficiency requirements.

Capital Market Reform

The CapitaI Market Reform is continuing in spite of delays due to the COVID-19 shock, as specified under the DCFTA agreement. The GoG intends to strengthen the regulatory framework for investment funds, funded-pension operations, market abuse and transparency, business conduct and custody and to transit gradually to a primary-dealer (PD) system in government securities market. For this purpose during the reporting period:

•	Investment Funds Law and related legal changes were adopted in summer by Parliament of Georgia. It has already been translated into English and published online on legislative herald of Georgia.

•	Securities Holding draft law is going through the last revisions with market participants until its submission to the parliament. Draft is expected to be submitted to the parliament shortly.

•	Work on Pillar 3 Pension Schemes draft law has started. With ADB’s technical assistance, an international expert was contracted and first consultation with market will be conducted during the fall. Introduction of the draft to the parliament is planned to take place in 2021.

•	Work on Securitization draft law has also commenced. International expert will be contracted by the end of September by USAID. A work plan has been submitted to the donor and is being reviewed. The introduction to the parliament is expected by late 2021.

•	Covered Bonds draft law is being drafted by National Bank of Georgia. Draft law is going through last revisions between NBG and market participants over specific items, such as technical mechanisms for bond issuance.

•	Capital Market Master Plan (Strategy). Table of content for the master plan has been set by consultant and public stakeholders and first workshop has been conducted between public and private market stakeholders. It is expected that strategy will be submitted for adoption to the government this Fall.

•	Research has commenced on Crowdfunding, Trust and Commodity Trading subjects.

•	Work concerning Primary Dealer System has begun and Ministry of Finance of Georgia along with National Bank of Georgia are receiving and examining requests from financial institutions on becoming primary dealers of the memorandum.

Education Reform

Georgia is undergoing a reform process in all the key directions of the education: Pre-school, General, Higher, Vocational Education and science. During the reporting period following important steps have been made:

•	Development of the Unified Strategy for Education and Science for the years 2022-2030 has been initiated. The process is actively supported by the European Union (Public Administration Reform Support Project).

•	Standard of Teacher Profession - Order of Minister of Georgia N67/n, was issued on 30/06/2020. The standard defines professional knowledge, skills, and obligations of a teacher. it serves as the foundation of the regulation of the teacher profession.

•	Amendments to the Government Ordinance N 241 (May 23, 2019) on Approving the Scheme for Professional Development and Career Advancement of Teachers was made (Ordinance of the Government of Georgia N390 issued on 26/06/2020). The document describes the Scheme for Teachers Professional Development and Career Advancement, which fully addresses the problems existing in the general education sector of Georgia and offers complex approaches for their resolution. It represents the ground for the state governance of the teacher’s profession. The Scheme serves the purpose of establishing the high - quality education system and is based on the principles of equality and fairness.

•	The GoG introduced reimbursement policy focused on increase in salary, which will motivate existing personnel to perform better and also encourage future teachers to enter the profession. Average salary for full-time workload according to the teacher status has increased: Practitioner – 526 GEL, Senior -1010 GEL, Lead -1415 GEL and Mentor -1745 GEL.

•	Basic salary (reimbursement in GEL/per hour) of VET teachers has increased and reached 11 GEL in 2019 and 15 GEL in 2020.

•	To upgrade the skills of the adult population and meet the demands of the labour market, the adult education system has been developed in the context of formal education. After completing short-term vocational training-retraining programmes a state-recognized certificate is issued. To improve competences and capacities of the lifelong learning, documents for regulation of non-formal education recognition have been developed and approved;

Infrastructure Development

The Government of Georgia continues developing core infrastructure network in the country to improve internal connectivity and support the strengthening of internal value chains in the country.

- It is planned that by the end of 2020, additional up to 70 km long section of highway will be constructed. From January to August, 2020, 46 km long different sections of highway have already been built and by the end of the year, additional 24 km section will be constructed (second line of Kutaisi bypass).

  - As a result by the end of 2020, average duration of travel time from Tbilisi to Batumi will be reduced up to 4 hours.

- Apart from the highway, the Government of Georgia has rehabilitated/repaired 285 km sections of the roads of interstate importance and rehabilitated/constructed 20 different bridges.

- At the same time, GoG has constructed/rehabilitated (some of them started in 2019 and ended in 2020 and some of them are still ongoing) more than 45 km (22.5 km ongoing) long different sections of the roads of local importance in different municipalities within the projects funded by the central state budget and by the development partners.

  - Additional 269 062 559 GEL is allocated for the road and bridge constructions (works have been/are being undertaken by the different municipalities).

Insolvency Reform

Insolvency reform is one of the key reform agenda areas for the GoG. This will be critical to deal with the aftermath of the COVID-19 shock. In this direction after having learned various insolvency systems and considering international best practice, a new law on Insolvency Proceedings has been prepared. The law largely differs from the previous law of Georgia on Insolvency Proceedings, introducing new mechanisms and making the process more flexible and efficient, providing adequate protection of creditor rights, timely and efficient insolvency processes and effective rehabilitation framework in line with best international standards.

The law is already adopted by the parliament (18.09.2020) and will enter into force from April 1st, 2021.

Main advantages of the law are the following:

•	Incentives for the rehabilitation of a debtor will be provided by the law, such as introducing debtor in possession institution, possibility of conversion of the bankruptcy proceeding into rehabilitation, suspension of a hearing a bankruptcy application until the decision on a rehabilitation application is made, etc.

•	United Registry of insolvency practitioners will be established ensuring the high level of professionalism of case managers;

•	The rights and responsibilities of case managers will be prescribed by the law in details in order to avoid vague and non-uniform practice etc.

•	Participation of all creditors, including unsecured creditors, will be ensured while voting on significant decisions for the company;

•	Certain amount of the claims of employees will be given preference in satisfaction with respect to other unsecured creditors;

•	Flexible means of selling insolvency property as an alternative to an auction will be provided by the law;

•	Voluntary arrangement mechanism will be introduced as a means of an out of court resolution of disputes etc.

Law on Entrepreneurs

Within the framework of the Private Law Reform Interagency Council, a new draft law of Georgia on Entrepreneurs is being processed, which aims to strengthen the role and purpose of law in entrepreneurial relations. For this reason, a number of norms should be introduced, which, on the one hand will strengthen the principle of charter autonomy and on the other hand will perform some sort of controlling function in the process of using such autonomy.

The draft law introduces dispositive norms, through which the parties will have the possibility to better regulate corporate relationships and besides, in case of the absence of appropriate regulations in the charter, there will be a proper normative basis, in order to avoid the legislative vacuum, which nowadays prevents the participants of this relationship and the court to duly review and resolve the case. Besides, the draft law comprises the norms of the relevant EU regulations envisaged by the Association Agreement between Georgia and the European Union and its annexes and through this, aims to fulfill the obligations under the Association Agreement and Association Agenda.

The draft is approved by the Government and is already submitted to the Parliament of Georgia.

# 4. Implementation

Taking into consideration the dynamic and complex nature of the problem, the implementation of the GACEP is resource intensive, which requires high level coordination and engagement of the respective state entities, follow-up monitoring activities as well as ensuring proper visibility actions so that the society is well-informed about the assistance packages.

## 4.1 Coordination Mechanism

For the effective Implementation of the GACEP, coordination is done by the existing Interagency Coordination Council on Covid-19. The council is chaired by the Prime-Minister of Georgia, was founded order to ensure an effective and coordinated fight against the coronavirus. The Council is the main decision-making platform on issues pertaining to the coronavirus. It is consists of members of the government, members of Parliament, the Administration of the President of Georgia and medical representatives.

One of the four priority directions in the fight against COVID-19, is the economy - The management and recovery of the Georgian economy in the face of the global economic crisis.

It was under this direction that the GACEP has been elaborated. The relevant member of the council were tasked by the prime-minister to develop Anti-Crisis Measures in their respective areas. After the rounds of the consultation the first consolidated draft of the GACEP was presented to the public in April 2020.

All these initiatives have been based on the consultations and recommendation by the local and international experts. By the support of the development partners, the government of Georgia has been able collect expertise and technical support from the leading international consultancies and experts.

During the implementation phase, all the responsible agencies are reporting to the abovementioned council, which gathers continuously once in a week. However, due to the complex nature of the problem, the council also gathers on ad-hoc basis in order to ensure that new and emerging challenges are dealt in timely manner.

## 4.2 Monitoring and Reporting Framework

For effective implementation of any government policy document rigorous monitoring is essential component. While on the other hand, government as public body should ensure its responsibility for the accountability by reporting on the progress of implementation in timely manner.

Monitoring aims to: Collect and analyze information on progress against the outcomes of objectives specified in any policy document; Regularly collect and analyze information on the implementation of activities specified in an action plan; and Based on collected information, identify achievements and shortcomings and develop relevant recommendations.

In 2019 Government of Georgia adopted landslide #629 Decree which established completely new Policy Development and Coordination System in the county, that is based on the European Principles of the Public Administration. Beside many novelties regarding evidence-based policy making process and introduction of the results-based management, the system also ensures establishment of the rigorous monitoring and evaluation framework for any policy document that is adopted by the government of the Georgia.

This regulations also applies to the GACEP – meaning that, despite the fact the nature and design of this document is a bit different (mostly short term operative document), the same monitoring instruments (such as for examples implementation rate) and reporting standards are applied.

In particular, following to the guidelines suggested by the #629 decree, two types of the monitoring reports will be produced:

- Progress Report (the present document)

- Annual Report (covering 1 year of implementation of the GACEP)

As identified in the handbook A progress report aims at providing the most recent information about activities in accordance with the action plan. Such reports are, as a rule, prepared, at least, once in six months. Progress reports are prepared only at the level of activities.

On the other hand the annual report needs to more analytical (rather than only as descriptive as progress report) and should must provide information on achieved results that are related not only to activities, but to objectives too.

Therefore, more analytical report, describing achievements and identifying possible impacts of the government interventions, will be developed after 1 year of inception of the GACEP.

## 4.3 Visibility and Communication

Proper and the simplified communication with the public is essential for the effective implementation of any plan, activity or intervention. Therefore, from the very beginning of the implementation of the GACEP all public entities, coordinated by the Administration of the Government, have been using all sorts of the instruments in order to get information delivered to each citizen or business company.

For that purpose a range of instruments have been used. In particular:

- Presentations in PPT format have been prepared

- Anti-crisis plan presentations, done by the Prime Minister and in some cases by the respective ministers, were live broadcasted

- Special video materials were prepared, that have been:

  - aired on TV

  - posted and boosted on social media

- In order to make the plan accessible to any person, the GACEP section have been developed and added to the special Covid-19 related state official web-page (WWW.STOPCOV.GE). The and respective detailed presentations have been uploaded.

- Presentations were also translated into English

- Info banners were made periodically (informative or showing results)

- News, videos, banners related to the anti-crisis plans were posted on the Georgian Government's social media platforms - Facebook, YouTube, the website of the GoG (posts were actively promoted on Facebook);

- The material was also posted on the social media of the relevant ministries and the regional self-governments;

- In the regions, news about the anti-crisis plan and compensation was delivered to the ethnic minorities in their native language, and informational meetings have been held.

- Citizens received text messages through their cell-phones.

In general, constant and proactive spread of the information has been considered as one of the main contributing factors of the Georgia’s success in the containment of the virus during the first wave, as much as informed citizens would be able to make informed decisions. The government has made sure that the all possible instruments have been set in motion for making all information available for the public.

# 5. Challenges and Recommendations

Covid-19 pandemic has also sharpened focus on resilience and emergency preparedness, with a strong accent on healthcare, social support and economic stability. At the moment of writing this report, the consequences of the outbreak at full extent still need to be comprehensively assessed. It is clear though, that international cooperation effort – both on a global and on a regional scale – will be required to effectively mitigate such risks in the future.

According to the IMF estimations Georgian economy is expected to shrink by 6% in 2020. Although the next year it is estimated that the economic growth will be back at the 6%, the general pessimistic global economic outlook will still significantly effect on Georgia’s social and economic development.

Despite the measures outlined in this report and positive results, (also through the support provided by the development partners), there are still gaps for the outstanding needs caused by pandemic.

Therefore, in medium and long-term perspective the country will require schemes for financing for the recovery phase.

Furthermore, incentives need to be considered for capturing new investment and market opportunities arisen from COVID-19 related global re-positioning of industries and long-term policy for competitiveness.

New and additional approaches need to identified in the tourism sector – as driving force of the Georgia’s economy. However, having somewhat grim picture of demand in the years to come in this area, the country needs to identify other economic areas for the development in medium-term perspective and ensure that support both from the state as well as development partners is effective in inviting the new investments.

Ambu bags, Dispisable shoe covers, Corpse bags, Contactless electric thermometers, Medical overalls, Disposable surgical gowns, Disposable Surgical Masks, Pulse Oximeters, Liquid medical oxygen, Respirator with valves, Respirator without valve, Disinfectant solution, Disinfectant solution, Individual protection goggles, Individual protection goggles, Individual protection goggles, FACE SHIELD, Disposable caps, Gloves.

Lab Tests, Medical scarifiers, Orient Gene COVID-19 IgG / IgM, COVID-19 Antigen Tests, Procurement of Qiagen RNA Mini Kit (250”) , Thermos Scientifics COVID-19 tests, Standard COVID-19 AG Test, Xpert Xpress SARS-CoV-2 kit

Nucleic Acid Diagnostic Kit, GeneMATRIX Viral RNA/DNA Purification Kit, MATRIX Viral RNA/DNA Purification Kit

AG/AB rapid tests, In Vitro Diagnostic Medical Device (cobas)

Defibrillators, Electronic extractors, Lineomats, Patient Monitors, Artificial respiration device, Critical Care Ventilators, Mobile Emergency Ventilators and Related Services MDS LTD 20 unit, CT scanners, Equipments for Primary Healthcare Facilities