SCOPE OF WORKS

CHIEF OF MISSION RESIDENCE (CMR)

MAKE READY /RENOVATIONS (FY 2018)

OVERVIEW

Client:

The United States Government (USG), Department of State (DOS), has a requirement to undertake roof retrofit and roof repairs, Staircase repairs, paving blocks repairs within the Chief of Mission Residence (CMR) compound.

Location/Contacts: Chief of Mission Residence (CMR) R2002- Muthaiga road, Nairobi, Kenya

OBJECTIVE

Requirements in this SOW serve as a direction to the Contractor undertaking roof retrofit and roof repairs. The Contractor shall perform all services in accordance with local and international safety and construction standards as generally applicable to accepted professional practices. The work shall be undertaken according to the list specifications. No variations /deviations will be implemented without prior approval from contracting officer (CO). Any foreseeable element likely to warrant cost adjustments must be discussed at the point of quotation.

TIME FRAME

Upon receipt of the order, the contractor shall be expected to submit work plan/Work break down, resource allocation ( tools, labor, materials, equipment…), time schedule (Gantt Chart),  through the COTR within 5 days, commence work within 7 days and must undertake the work as per the agreed upon schedule.

APPLICABLE STANDARDS

1.	Local Building codes: the local government (adoptive by-laws)

(Building) order 1968

2.	Local Safety regulations: OSHA 2007 (safety compliance)

3.	Nairobi city Council by laws (operational compliance)

4.	NEMA by-laws (in safe disposal of waste)

5.	US safety regulations: US Army corps of Engineers

6. 	 Other applicable regulations: See clauses in section H below.

SPECIAL REQUIREMENTS

- Access into the USG premises is at the discretion of the Regional Security office and therefore approval must be obtained at least 24hours before date entry.

- Work must be done under escort of the appropriate clearance level as applicable in the space concerned.

- Work schedule must be done in such a way that the chancery operations has least impact. The schedule and construction logistics must be discussed and approved through the COR.

- Vendor has the responsibility to obtain all relevant approval from respective regulatory bodies including but not limited to: Nairobi City County (NCC), NEMA.

SCOPE OF WORK

|  | R2002 RETROFITTING A PITCHED ROOF OVER A FLAT ROOFED GARAGE AND KITCHEN |  |  |
| --- | --- | --- | --- |
| Item | Description | Unit | QTY |
| 1 | Clear the existing roof and gutter off any leaves and debris in preparation for commencement of roof works,test and leave the gutters in working condition. | SM | 70 |
| 2 | Design,supply and fabricate: light gauge steel trusses,rafters and purlins and position to receive new stone coated roofing tiles. | SM | 100 |
| 3 | Supply and install new gauge 24 stone coated steel sheet roofing tiles to match the residence profile and colour | SM | 100 |
| 4 | Ditto for ridge | LM | 15 |
| 5 | Ditto for badgeboard covers | LM | 30 |
| 6 | Fabricate gable sides 4 no from well seasoned cypress T&G varnished to match existing with three concealed access doors. | SM | 30 |
| 7 | ditto for eaves but to match the existing house design | SM | 10 |
| 8 | Allow for construction of chimney cricket and extension of existing chiney hood to form chimney | LS | 1 |
| 9 | Supply and install new 200MM X 25MM fascia boards painted to match the existing house colour profile | LM | 30 |
| 10 | Supply and install water goods pre-painted 200 mm G.I/Alu-zinc gutters 22G x 100 x 75 mm box gutter | LM | 25 |
| 11 | Supply and install down pipe with shoe 160 mm diameter | LM | 10 |
| 12 | Remove the existing foot traffic damaged roof tiles | SM | 150 |
| 13 | Supply and install new gauge 24 stone coated steel sheet roofing tiles to match the residence profile and colour | SM | 150 |
| 14 | Clear all debris from site | LS | 1 |

|  | Stair Case Railing Work/Cabro repairs/Grilles &safe havens |  |  |
| --- | --- | --- | --- |
| NO | DESCRIPTION | UNIT | QTY |
| 1 | Fabricating and installing in position railing as per the given design. The height of the railing shall be 1200 mm from the respective finished floor level. (a) 50mmx25mm RHS top rail and ditto for bottom rail b) 50mmx25mm RHS as main vertical members spaced at 100mm center to center height 900mm c) 150x150mm wooden balusters height 1200 mm fixed to ground 4 no Incl. providing & applying at least three coats of paint of approved quality & tint, welding, grinding, finishing, hydraulically bending etc. complete as directed by CORT | LM | 20.00 |
| 2 | Remove existing stone work steps and supply and lay bush hammered stonework Grey quarry stone on the steps as shown on site | SM | 25.00 |
| 3 | Supply all labor material and equipment to repair walk path low spots, uneven levels, loose edgings, puddle areas and broken paving blocks as shown on site. This shall be accomplished by removing the blocks on affected areas, repairing the bedding and sub Base (remove old sand, adding new sand layer and compact),correct the levels, relay the pavers allow for replacing broken ones 60mm thick, reconsolidate the area, compact and apply sand to fill the new joints. Area affected = 250sqm | SM | 250.00 |

| 4 | Grill door / safe haven spacings |  |  |
| --- | --- | --- | --- |
| a. | Supply, cut to size and weld hammered metal to match existing as per the specifications on the upstairs grill doors and the safe haven grill. 16mm. | Lengths | 5 |
| b. | Grind smooth the welded edges and fill in | item | item |
| c. | Paint to match the existing and make good all affected parts. | item | item |
| d. | Cover all areas to provide protection to the wall and floor. | item | Item. |
| e. | Hot works permit signed by the POSHO and all hot works procedure to be adhered to. |  |  |

WORKMANSHIP STANDARDS

The CONTRACTOR confirms that he is an expert in this field of work and is fully knowledgeable and experienced in all aspects of procedures, methods, regulations, codes and municipal requirements and the CONTRACTOR further acknowledges that the OWNER is relying on this expertise.
Care shall be taken to ensure that the base surfaces are properly prepared and that the materials are used correctly.

General requirements

1. All work is to comply with the local building regulations.

2. The contractor will rectify any damage to all areas on completion of the works.

3. The contractor shall supply all materials and labour in order to complete the works.

4. All waste material to be taken from site and disposed of by the contractor.

5. Site is to remain tidy at all times and cleaned up on completion of works.

7. All Documentation regarding warranties, guarantees and instructional literature are to be handed to your COR.

9. Any variations are to be priced and approved in writing by CO before proceeding with the work.

10. All measurements are to be confirmed by the contractor on site.

11. Work is expected to happen during the weekend due to the nature of office operations and therefore work program must factor the aspect sufficiently

NOTE: Any damage caused by the Contractor or his contractors is to be made good at the Contractor’s expense.

NOTE:

- A 12 MONTHS GUARANTEE ON ALL THE IS REQUIRED.

- If Contractor fails to perform as per specification of this, the Contractor shall indemnify the Government from any and all claims arising therefrom.

C.	PACKAGING AND MARKING

Materials delivered to the site as follows:

AMERICAN EMBASSY – R2002 (CMR)

D.        INSPECTION AND ACCEPTANCE

(See attached Performance/Completion evaluation form)

The COR, or his/her authorized representatives, will inspect from time to time the services being performed and the supplies furnished to determine whether work is being performed in a satisfactory manner, and that all supplies are of acceptable quality and standards.

The Contractor shall be responsible for any countermeasures or corrective action, within the scope of this contract, which may be required by the Contracting Officer as a result of such inspection.

Substantial Completion:  Definitions

(a) "Substantial Completion" means the stage in the progress of the work as determined and certified by the Contracting Officer in writing to the Contractor, on which the work (or a portion designated by the Government) is sufficiently complete and satisfactory.  Substantial completion means that the property may be occupied or used for the purpose for which it is intended, and only minor items such as touch-up, adjustments, and minor replacements or installations remain to be completed or corrected which:

(1) Do not interfere with the intended occupancy or utilization of the work, and

(2) Can be completed or corrected within the time period required for final completion.

(b) The "date of substantial completion" means the date determined by the Contracting Officer or authorized Government representative as of which substantial completion of the work has been achieved.

Use and Possession upon Substantial Completion

The Government shall have the right to take possession of and use the work upon substantial completion.  Upon notice by the Contractor that the work is substantially complete (a Request for Substantial Completion) and an inspection by the Contracting Officer or an authorized Government representative (including any required tests), the Contracting Officer shall furnish the Contractor a Certificate of Substantial Completion.  The certificate will be accompanied by a Schedule of Defects listing items of work remaining to be performed, completed or corrected before final completion and acceptance.  Failure of the Contracting Officer to list any item of work shall not relieve the Contractor of responsibility for complying with the terms of the contract.  The Government's possession or use upon substantial completion shall not be deemed an acceptance of any work under the contract.

Final Completion and Acceptance:  Definitions

(a) "Final completion and acceptance" means the stage in the progress of the work as determined by the Contracting Officer and confirmed in writing to the Contractor, at which all work required under the contract has been completed in a satisfactory manner, subject to the discovery of defects after final completion, and except for items specifically excluded in the notice of final acceptance.

(b) The "date of final completion and acceptance" means the date determined by the Contracting Officer when final completion of the work has been achieved, as indicated by written notice to the Contractor.

Final Inspection and Tests

The Contractor shall give the Contracting Officer at least five (5) days advance written notice of the date when the work will be fully completed and ready for final inspection and tests.  Final inspection and tests will be started not later than the date specified in the notice unless the Contracting Officer determines that the work is not ready for final inspection and so informs the Contractor.

Final Acceptance

If the Contracting Officer is satisfied that the work under the contract is complete (with the exception of continuing obligations), the Contracting Officer shall issue to the Contractor a notice of final acceptance and make final payment upon:

-Satisfactory completion of all required tests,

-a final inspection that all items by the Contracting Officer listed in the Schedule of Defects have been completed or corrected and that the work is finally complete (subject to the discovery of defects after final completion), and

-submittal by the Contractor of all documents and other items required upon completion of the work, including a final request for payment (Request for Final Acceptance).

E - DELIVERIES OR PERFORMANCE

52.211-10  COMMENCEMENT, PROSECUTION, AND COMPLETION OF WORK

(APR 1984)

The Contractor shall be required to:

(a)    Commence work under this contract within 5 calendar days after the date the Contractor receives the notice to proceed,

(b)   Prosecute the work diligently, and,

(c)    Complete the entire work ready for use not later than 8 weeks for interior doors, 5 weeks for ceiling replacement, 10 weeks for kitchen replacement and 6 weeks for closet replacement after receipt of notice to proceed.

The time stated for completion shall include final cleanup of the premises and completion of punch list items.

CONTRACTOR'S SUBMISSION OF CONSTRUCTION SCHEDULES

(a)	The time for submission of the schedules referenced in FAR 52.236-15, "Schedules for Construction Contracts", paragraph (a), is hereby modified to reflect the due date for submission as 5 calendar days after receipt of an executed contract".
	(b)	These schedules shall include the time by which shop drawings, product data, samples and other submittals required by the contract will be submitted for approval.   
	(c)	The Contractor shall revise such schedules (1) to account for the actual progress of the work, (2) to reflect approved adjustments in the performance schedule, and (3) as required by the Contracting Officer to achieve coordination with work by the Government and any separate contractors used by the Government.  The Contractor shall submit a schedule, which sequences work so as to minimize disruption at the job site. 
	(d)	All deliverables shall be in the English language and any system of dimensions (English or metric) shown shall be consistent with that used in the contract.  No extension of time shall be allowed due to delay by the Government in approving such deliverables if the Contractor has failed to act promptly and responsively in submitting its deliverables.  The contractor shall identify each deliverable as required by the contract.

(e)	Acceptance of Schedule:  When the Government has accepted any time schedule; it shall be binding upon the Contractor.  The completion date is fixed and may be extended only by a written contract modification signed by the Contracting Officer.  Acceptance or approval of any schedule or revision thereof by the Government shall not:

(1)   Extend the completion date or obligate the Government to do so,

(2)   Constitute acceptance or approval of any delay, or

(3)   Excuse the Contractor from or relieve the Contractor of its obligation to maintain the progress of the work and achieve final completion by the established completion date.

Notice Of Delay

If the Contractor receives a notice of any change in the work, or if any other conditions arise which are likely to cause or are actually causing delays which the Contractor believes may result in late completion of the project, the Contractor shall notify the Contracting Officer.  The Contractor’s notice shall state the effect, if any, of such change or other conditions upon the approved schedule, and shall state in what respects, if any, the relevant schedule or the completion date should be revised.  The Contractor shall give such notice promptly, not more than ten (10) days after the first event giving rise to the delay or prospective delay. Only the Contracting Officer may make revisions to the approved time schedule.

Notice to Proceed

(a)	After receiving and accepting any bonds or evidence of insurance, the Contracting Officer will provide the Contractor a Notice to Proceed.  The Contractor must then prosecute the work, commencing and completing performance not later than the time period established in the contract.
	(b)	It is possible that the Contracting Officer may elect to issue the Notice to Proceed before receipt and acceptance of any bonds or evidence of insurance.  Issuance of a Notice to Proceed by the Government before receipt of the required bonds or insurance certificates or policies shall not be a waiver of the requirement to furnish these documents.

Working Hours

All work shall be performed during regular working hours.  Other hours, if requested by the Contractor, may be approved by the Contracting Officer's Representative (COR).  The Contractor shall give 24 hours in advance to COR who will consider any deviation from the hours identified above.  Changes in work hours, initiated by the Contractor, will not be a cause for a price increase.

Preconstruction Conference

A preconstruction conference will be held 2 days after contract award at the American Embassy, Nairobi to discuss the schedule, submittals, notice to proceed, mobilization and other important issues that affect construction progress.  See FAR 52.236-26, Preconstruction Conference.

Deliverables
The following items shall be delivered under this contract:

Description				Quantity	Delivery Date		Deliver to:

G.  Securities/Insurance		1		5 days after award	Contracting Officer

E. Construction Schedule		1		2 days after award	COR

E   Preconstruction Conference	1		2 days after award 	COR

G.  Personnel Biographies		1		5 days after award	COR

F.  Payment Request		1		last calendar day of	COR

each month

D. Request for Substantial Completion 1		15 days before inspection COR

D Request for Final Acceptance	1		5 days before inspection COR

F  ADMINISTRATIVE DATA

652.242-70 CONTRACTING OFFICER'S REPRESENTATIVE (COR) (AUG 1999)

(a)	The Contracting Officer may designate in writing one or more Government employees, by name or position title, to take action for the Contracting Officer under this contract. Each designee shall be identified as a Contracting Officer’s Representative (COR). Such designation(s) shall specify the scope and limitations of the authority so delegated; provided, that the designee shall not change the terms or conditions of the contract, unless the COR is a warranted Contracting Officer and this authority is delegated in the designation.

(b)	The COR for this contract is the Contracting officer.

Payment: The Contractor's attention is directed to Section H, 52.232-5, "Payments Under Fixed-Price Construction Contracts".  The following elaborates on the information contained in that clause.

Requests for payment, may be made no more frequently than monthly.  Payment requests shall cover the value of labor and materials completed and in place, including a prorated portion of overhead and profit.

After receipt of the Contractor's request for payment, and on the basis of an inspection of the work, the Contracting Officer shall make a determination as to the amount, which is then due.  If the Contracting Officer does not approve payment of the full amount applied for, less the retainage allowed by in 52.232-5, the Contracting Officer shall advise the Contractor as to the reasons.

Under the authority of 52.232-27(a), the 14 day period identified in FAR 52.232-27(a)(1)(i)(A) is hereby changed to 30 days.

The contractor shall show Value Added Tax (VAT) as a separate item on invoices submitted for payment.

G. SPECIAL REQUIREMENTS

Insurance

The Contractor is required by FAR 52.228-5, "Insurance - Work on a Government Installation" to provide whatever insurance is legally necessary.  The Contractor shall at its own expense provide and maintain during the entire performance period the following insurance amounts:
	General Liability (includes premises/operations, collapse hazard, products, completed operations, contractual, independent contractors, broad form property damage, personal injury)
	The foregoing types and amounts of insurance are the minimums required.  The Contractor shall obtain any other types of insurance required by local law or that are ordinarily or customarily obtained in the location of the work.  The limit of such insurance shall be as provided by law or sufficient to meet normal and customary claims.

The Contractor agrees that the Government shall not be responsible for personal injuries or for damages to any property of the Contractor, its officers, agents, servants, and employees, or any other person, arising from and incident to the Contractor's performance of this contract.  The Contractor shall hold harmless and indemnify the Government from any and all claims arising therefrom, except in the instance of gross negligence on the part of the Government.

The Contractor shall obtain adequate insurance for damage to, or theft of, materials and equipment in insurance coverage for loose transit to the site or in storage on or off the site.

The general liability policy required of the Contractor shall name "the United States of America, acting by and through the Department of State", as an additional insured with respect to operations performed under this contract.

Document Descriptions

Supplemental Documents:  The Contracting Officer shall furnish from time to time such detailed drawings and other information as is considered necessary, in the opinion of the Contracting Officer, to interpret, clarify, supplement, or correct inconsistencies, errors or omissions in the Contract documents, or to describe minor changes in the work not involving an increase in the contract price or extension of the contract time.  The Contractor shall comply with the requirements of the supplemental documents, and unless prompt objection is made by the Contractor within 20 days, their issuance shall not provide for any claim for an increase in the Contract price or an extension of contract time.

Record Documents.  The Contractor shall maintain at the project site:

(1)  a current marked set of Contract drawings and specifications indicating all interpretations and clarification, contract modifications, change orders, or any other departure from the contract requirements approved by the Contracting Officer; and,

(2)  a complete set of record shop drawings, product data, samples and other submittals as approved by the Contracting Officer.

"As-Built" Documents:  After final completion of the work, but before final acceptance thereof, the Contractor shall provide:

(1)  a complete set of "as-built" drawings, based upon the record set of drawings, marked to show the details of construction as actually accomplished; and,

(2)  Record shop drawings and other submittals, in the number and form as required by the specifications.

Laws and Regulations

The Contractor shall, without additional expense to the Government, be responsible for complying with all laws, codes, ordinances, and regulations applicable to the performance of the work, including those of the host country, and with the lawful orders of any governmental authority having jurisdiction.  Host country authorities may not enter the construction site without the permission of the Contracting Officer.  Unless otherwise directed by the Contracting Officer, the Contractor shall comply with the more stringent of the requirements of such laws, regulations and orders and of the contract.  In the event of a conflict between the contract and such laws, regulations and orders, the Contractor shall promptly advise the Contracting Officer of the conflict and of the Contractor's proposed course of action for resolution by the Contracting Officer.

The Contractor shall comply with all local labor laws, regulations, customs and practices pertaining to labor, safety, and similar matters, to the extent that such compliance is not inconsistent with the requirements of this contract.

The Contractor shall give written assurance to the Contracting Officer that all subcontractors and others performing work on or for the project have obtained all requisite licenses and permits.

The Contractor shall submit proper documentation and evidence satisfactory to the Contracting Officer of compliance with this clause.

Construction Personnel

The Contractor shall maintain discipline at the site and at all times take all reasonable precautions to prevent any unlawful, riotous, or disorderly conduct by or among those employed at the site.  The contractor shall ensure the preservation of peace and protection of persons and property in the neighborhood of the project against such action.  The Contracting Officer may require, in writing that the Contractor remove from the work any employee that the Contracting Officer deems incompetent, careless, insubordinate or otherwise objectionable, or whose continued employment on the project is deemed by the Contracting Officer to be contrary to the Government's interests.

If the Contractor has knowledge that any actual or potential labor dispute is delaying or threatens to delay the timely performance of this contract, the Contractor shall immediately give notice, including all relevant information, to the Contracting Officer.

After award, the Contractor has 5 calendar days to submit to the Contracting Officer a list of workers and supervisors assigned to this project for the Government to conduct all necessary security checks.  It is anticipated that security checks will take 10 days to perform.  For each individual the list shall include:

Full Name

Place and Date of Birth

Current Address

Identification number

Morality Certificate

Failure to provide any of the above information may be considered grounds for rejection and/or re-submittal of the application.  Once the Government has completed the security screening and approved the applicants a badge will be provided to the individual for access to the site. This badge may be revoked at any time due to the falsification of data, or misconduct on site.

The Contractor shall provide an English speaking supervisor on site at all times.  This position is considered as key personnel under this purchase order.

Materials and Equipment

All materials and equipment incorporated into the work shall be new and for the purpose intended, unless otherwise specified.  All workmanship shall be of good quality and performed in a skillful manner that will withstand inspection by the Contracting Officer.

Special Warranties

Any special warranties that may be required under the contract shall be subject to the stipulations set forth in 52.246-21, "Warranty of Construction", as long as they are not in conflict.
	The Contractor shall obtain and furnish to the Government all information required to make any subcontractor's, manufacturer's, or supplier's guarantee or warranty legally binding and effective.  The contractor shall submit both the information and the guarantee or warranty to the Government in sufficient time to permit the Government to meet any time limit specified in the guarantee or warranty, but not later than completion and acceptance of all work under this contract.

Equitable Adjustments

Any circumstance for which the contract provides an equitable adjustment that causes a change within the meaning of paragraph (a) of the "Changes" clause shall be treated as a change under that clause; provided, that the Contractor gives the Contracting Officer prompt written notice (within 20 days) stating:

(a)    The date, circumstances, and applicable contract clause authorizing an equitable adjustment and

(b)   That the Contractor regards the event as a changed condition for which an equitable adjustment is allowed under the contract.

The Contractor shall provide written notice of a differing site condition within 10 calendar days of occurrence following FAR 52.236-2, Differing Site Conditions.

Zoning Approvals and Permits

The Government shall be responsible for:

- Obtaining proper zoning or other land use control approval for the project

- Obtaining the approval of the Contracting Drawings and Specifications

- paying fees due for the foregoing; and,

- Obtaining and paying for the initial building permits.

- Provide power required to facilitate construction and installation work.

- Arrange for access and escort where required.

H. CLAUSES

52.252-2 CLAUSES INCORPORATED BY REFERENCE (FEB 1998)

This contract incorporates one or more clauses by reference, with the same force and effect as if they were given in full text. Upon request, the Contracting Officer will make their full text available. Also, the full text of a clause may be accessed electronically at this/these address(es):

http://www.arnet.gov/far   or,   http://farsite.hill.af.mil/search.htm

These addresses are subject to change.  If the Federal Acquisition Regulation (FAR) is not available at the locations indicated above, use the Dept. of State Acquisition Website at http://www.statebuy.gov/home.htm to see the links to the FAR.   You may also use an Internet “search engine” (e.g., Yahoo, Excite, Alta Vista, etc.) to obtain the latest location of the most current FAR.

FEDERAL ACQUISITION REGULATION (48 CFR CH. 1)

Clause			Title and Date

52.209-6		Protecting the Government's Interest When Subcontracting with

Contractors Debarred, Suspended, or Proposed for Debarment

(JAN 2005)

52.213-4		Terms and Conditions-Simplified Acquisitions (Other than Commercial

Items) (MAR 2005)

52.222-1                                           Notice to the Government of Labor Disputes (FEB 1997)

52.222-19	Child Labor – Cooperation with Authorities and Remedies (JAN 2004)

52.225-10                                       Notice of Buy American Act/Balance of Payments Program—

Construction Materials  (FEB 2000)

52.225-13		Restrictions on Certain Foreign Purchases (MAR 2005)

52.225-14		Inconsistency Between English Version and Translation of

Contract (AUG 1989)

52.228-4		Workers’ Compensation and War-Hazard Insurance Overseas (APR 1984)

52.228-5		Insurance - Work on a Government Installation (JAN 1997)

52.228-11 		Pledges of Assets (FEB 1990)

52.228-13		Alternative Payment Protection (JUL 2000)

52.229-6		Taxes - Foreign Fixed-Price Contracts (JUN 2003)

52.232-5		Payments under Fixed-Price Construction Contracts (SEP 2002)

52.232-8		Discounts for Prompt Payment (FEB 2002)

52.232-11		Extras (APR 1984)

52.232-18	Availability of Funds (APR 1984)

52.232-24		Prohibition of Assignment of Claims (JAN 1986)

52.232-27		Prompt Payment for Construction Contracts (OCT 2003)

52.232-34		Payment by Electronic Funds Transfer – Other than Central Contractor Registration (MAY 1999)

52.233-1		Disputes (JUL 2002) Alternate I (DEC 1991)

52.233-3		Protest after Award (AUG 1996)

52.236-2		Differing Site Conditions (APR 1984)

52.236-3		Site Investigation and Conditions Affecting the Work (APR 1984)

52.236-5		Material and Workmanship (APR 1984)

52.236-6		Superintendence by the Contractor (APR 1984)

52.236-7		Permits and Responsibilities (NOV 1991)

52.236-8		Other Contracts (APR 1984)

52.236-9		Protection of Existing Vegetation, Structures,

Equipment, Utilities, and Improvements (APR 1984)

52.236-10		Operations and Storage Areas (APR 1984)

52.236-11		Use and Possession Prior to Completion (APR 1984)

52.236-12		Cleaning Up (APR 1984)

52.236-14		Availability and Use of Utility Services (APR 1984)

52.236-15		Schedules for Construction Contracts (APR 1984)

52.236-21		Specifications and Drawings for Construction  (FEB 1997)

52.236-26 		Preconstruction Conference (FEB 1995)

52.242-14		Suspension Of Work (APR 1984)

52.243-4		Changes (AUG 1987)

52.243-5		Changes and Changed Conditions (APR 1984)

52.244-6		Subcontracts for Commercial Items (MAR 2005)

52.245-4   		Government-Furnished Property (Short Form) (JUN 2003)

52.246-12			  Inspection of Construction (AUG 1996)

52.246-21		Warranty of Construction (APR 1984)

52.249-2                                           Termination for Convenience of the Government (Fixed-Price)

(MAY 2004) Alternate I (APR 1984)

52.249-10 		Default (Fixed-Price Construction) (APR 1984)

The following clauses are set forth in full text:

DEPARTMENT OF STATE ACQUISITION REGULATION (DOSAR) CLAUSES

652.242-73  AUTHORIZATION AND PERFORMANCE (AUG 1999)

(a) The contractor warrants the following:

(1) That is has obtained authorization to operate and do business in the country or countries in which this contract will be performed;

(2) That is has obtained all necessary licenses and permits required to perform this contract; and,

(3) That it shall comply fully with all laws, decrees, labor standards, and regulations of said country or countries during the performance of this contract.

(b) If the party actually performing the work will be a subcontractor or joint venture partner, then such subcontractor or joint venture partner agrees to the requirements of paragraph (a) of

this clause.

652.228-70	INDEMNIFICATION (JULY 1988)

The Contractor expressly agrees to indemnify and to save the Government, its officers, agents, servants, and employees harmless from and against any claim, loss, damages, injury, and liability, however caused, resulting from or arising out of the Contractor's fault or negligence in connection with the performance of work under this contract.  Further, any negligence or alleged negligence of the Government, its officers, agents, servants, or employees, shall not bar a claim for indemnification unless the act or omission of the Government, its officers, agents, servants, or employees is the sole competent, and producing cause of such claim, loss, damages, injury, or liability.

652.243-70  NOTICES (AUG 1999)

Any notice or request relating to this contract given by either party to the other shall be in writing. Said notice or request shall be mailed or delivered by hand to the other party at the address provided in the schedule of the contract. All modifications to the contract must be made in writing by the contracting officer.

652.229-71  PERSONAL PROPERTY DISPOSITION AT POSTS ABROAD (AUG 1999)

Regulations at 22 CFR Part 136 require that U.S. Government employees and their families do not profit personally from sales or other transactions with persons who are not themselves entitled to exemption from import restrictions, duties, or taxes. Should the contractor experience importation or tax privileges in a foreign country because of its contractual relationship to the United States Government, the contractor shall observe the requirements of 22 CFR

Part 136 and all policies, rules, and procedures issued by the chief of mission in that foreign country.

I. LIST OF ATTACHMENTS

None

J. QUOTATION INFORMATION

A.	QUALIFICATIONS OF OFFERORS

Offerors/quoters must be technically qualified and financially responsible to perform the work described in this solicitation.  At a minimum, each Offeror/Quoter must meet the following requirements:

(1)	Be able to understand written and spoken English;

(2)	Have an established business with a permanent address and telephone listing;

(3) 	Be able to demonstrate prior construction experience with suitable references;

(4)	Have the necessary personnel, equipment and financial resources available to perform the work;

(5)	Have all licenses and permits required by local law;

(6) 	Meet all local insurance requirements;

(7) 	Have the ability to obtain or to post adequate performance security, such as bonds, irrevocable letters of credit or guarantees issued by a reputable financial institution;

(8)	Have no adverse criminal record; and

(9)	Have no political or business affiliation which could be considered contrary to the interests of the United States.

B.	SUBMISSION OF QUOTATIONS

This solicitation is for the performance of the construction services described in SCOPE OF WORK, and the Attachments which are a part of this request for quotation.

Each quotation must consist of the following:

Volume                     Title                                                                 				  No. of Copies*

1. Standard Form 1442 Solicitation, Offer and Award (Construction, Alteration

or Repair)

2. Price Proposal and Completed Section B.  The Price Proposal shall include a

Breakdown of Proposal price by Division of Specifications

3.  Performance of a schedule in the form of a bar chart and Business Management/Technical   Proposal

Submit the complete quotation to the address indicated on Standard Form 1442, if mailed, or the address set forth below, if hand delivered.

Contracting Officer

American Embassy

GSO Procurement

US Embassy Nairobi

The Offeror/Quoter shall identify and explain/justify any deviations, exceptions, or conditional assumptions taken with respect to any of the instructions or requirements of this request for quotation in the appropriate volume of the offer.

Volume II: Performance schedule and Business Management/Technical Proposal.

(a)	Present the performance schedule in the form of a "bar chart" indicating when the various portions of the work will be commenced and completed within the required schedule.  This bar chart shall be in sufficient detail to clearly show each segregable portion of work and its planned commencement and completion date.

(b)	The Business Management/Technical Proposal shall be in two parts, including the following information:

Proposed Work Information - Provide the following:

(1) A list of the names, addresses and telephone numbers of the owners, partners, and principal officers of the Offeror;

(2) The name and address of the Offeror's field superintendent for this project;

(3) A list of the names, addresses, and telephone numbers of subcontractors and principal materials suppliers to be used on the project, indicating what portions of the work will be performed by them; and,

(4) Bar chart indicating various portions of the work; when work will commence and be completed in each section.

Experience and Past Performance - List all contracts and subcontracts your company has held over the past three years for the same or similar work.  Provide the following information for each contract and subcontract:

(1) Customer's name, address, and telephone numbers of customer's lead contract and technical personnel;

(2) Contract number and type;

(3) Date of the contract award place(s) of performance, and completion dates;

Contract dollar value;

(4) Brief description of the work, including responsibilities; and

(5) Any litigation currently in process or occurring within last 5 years.

C.`52.236-27	SITE VISIT (FEB 1995)

(a)	The clauses at 52.236-2, Differing Site Conditions, and 52.236-3, Site Investigations and Conditions Affecting the Work, will be included in any contract awarded as a result of this solicitation.  Accordingly, offerors or quoters are urged and expected to inspect the site where the work will be performed.

(b)	A site visit date shall be communicated through GSO Procurement, US Embassy Nairobi.

(c)	Participants will COR and Procurement agent for walk through.

D. `MAGNITUDE OF CONSTRUCTION PROJECT

# E.                  LATE QUOTATIONS.  Late quotations shall be handled in accordance with FAR

F.  52.252-1 SOLICITATION PROVISIONS INCORPORATED BY REFERENCE (FEB 1998)

This contract incorporates the following provisions by reference, with the same force and effect as if they were given in full text.  Upon request, the Contracting Officer will make their full text available.  The offeror is cautioned that the listed provisions may include blocks that must be completed by the offeror and submitted with its quotation or offer.  In lieu of submitting the full text of those provisions, the offeror may identify the provision by paragraph identifier and provide the appropriate information with its quotation or offer.

FEDERAL ACQUISITION REGULATION (48 CFR CH. 1)

52.215-1 INSTRUCTIONS TO OFFERORS--COMPETITIVE ACQUISITION (JAN 2004), which is incorporated by reference into this solicitation.

## K. EVALUATION CRITERIA

Award will be made to the lowest priced, acceptable, responsible quoter.  The Government reserves the right to reject quotations that are unreasonably low or high in price.

The Government will determine acceptability by assessing the offeror's compliance with the terms of the RFQ.  The Government will determine responsibility by analyzing whether the apparent successful quoter complies with the requirements of FAR 9.1, including:

- Ability to comply with the required performance period, taking into consideration all existing commercial and governmental business commitments;

- Satisfactory record of integrity and business ethics;

- Necessary organization, experience, and skills or the ability to obtain them;

- Necessary equipment and facilities or the ability to obtain them; and

- Otherwise qualified and eligible to receive an award under applicable laws and regulations.

- Full understanding of the scope of work through the proposal. The vendor must indicate clearly how he/she intends to overcome challenges including but not limited to: weather, local regulations, material handling and movement, environmental friendliness, traffic, minimum interruption to embassy operations.

- Capacity to deliver the required services

  - Human resource capacity

  - Equipment/Tools

  - Technical Capacity

  - Must be a road works specialist with at least 3 satisfactorily complete, recent jobs within the last three years. Contacts of satisfied customers’ point of contact are required.

- Methodology is compliant to the site

  - Sound sequence of operations fitted within a realistic period

  - Clear quality control plan and operationally feasible schedule favorable to embassy operations

  - Reliable measurement methods

- Provision of reasonable/fair warranty terms which are expressly communicated.

- National Construction Authority (NCA) registered contractor of class NCA 3 and higher.

L. REPRESENTATIONS, CERTIFICATIONS AND OTHER STATEMENTS OF OFFERORS OR QUOTERS

L.1	52.204-3 TAXPAYER IDENTIFICATION (OCT 1998) – N/A

L.2	52.204-6  CONTRACTOR IDENTIFICATION NUMBER -DATA UNIVERSAL NUMBERING SYSTEM (DUNS) NUMBER (OCT 2003) – N/A

L.3     52.204-8   ANNUAL REPRESENTATIONS AND CERTIFICATIONS

(JAN 2005) – N/A

L.4	AUTHORIZED CONTRACT ADMINISTRATOR

If the offeror does not fill-in the blanks below, the official who signed the offer will be deemed to be the offeror's representative for Contract Administration, which includes all matters pertaining to payments.

Name:    _________________________________________________

Address: _________________________________________________

_________________________________________________

Telephone Number: ________________________________________

L.5	DEFENSE BASE ACT INSURANCE – COVERED CONTRACTOR EMPLOYEES

(a)  Bidders/Offerors shall indicate below whether or not any of the following categories of employees will be employed on the resultant contract, and, if so, the number of such employees:

| Category | Yes/No | Number |
| --- | --- | --- |
| (1) United States citizens or residents |  |  |
| (2) Individuals hired in the United States, regardless of citizenship |  |  |
| (3) Local nationals or third country nationals where contract performance takes place in a country where there are no local workers’ compensation laws |  | Local nationals: ______________ Third Country Nationals: _____________ |
| (4) Local nationals or third country nationals where contract performance takes place in a country where there are local workers’ compensation laws |  | Local nationals: ______________ Third Country Nationals: _____________ |

(b)  If the bidder/offeror has indicated “yes” in block (a)(4) of this provision, the bidder/offeror shall submit, as part of its offer, a statement that indicates that such local nationals and/or third country nationals will be provided workers’ compensation coverage against the risk of work injury or death under a local workers’ compensation law.  For those employees, the bidder/offeror shall also assume liability toward the employees and their beneficiaries for war-hazard injury, death, capture, or detention, in accordance with the clause at FAR 52.228-4.

(c)  If the bidder/offeror has indicated “yes” in blocks (a)(1), (2), or (3) of this provision, the bidder/offeror shall compute Defense Base Act insurance costs covering those employees pursuant to the terms of the contract between the Department of State and the Department’s Defense Base Act insurance carrier at the rates specified in DOSAR 652.228-74.  If DOSAR provision 652.228-74 is not included in this solicitation, the bidder/offeror shall notify the contracting officer before the closing date so that the solicitation can be amended accordingly.

PERFORMANCE/COMPLETION CERTIFICATE

| PERFORMANCE EVALUATION CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract No |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PART 1 – GENERAL CONTRACT DATA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. TYPE OF EVALUATION INTERIM (List percentage______%) Final Amended |  |  |  |  |  |  |  |  |  |  |  |  |  | 4. TERMINATED FOR DEFAULT |  |  |  |  |  |  |  |  |  |
| 5. CONTRACTOR (Name, Address, and ZIP Code) |  |  |  |  |  |  |  |  |  |  |  | 6.a. PROCUREMENT METHOD SEALED BID NEGOTIATED |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | b. TYPE OF CONTRACT Firm fixed price Cost Reimbursement OTHER (Specify) |  |  |  |  |  |  |  |  |  |  |  |
| 7. DESCRIPTION AND LOCATION OF WORK (hit enter to wrap text |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. TYPE AND PERCENT OF SUBCONTRACTING Direct contractor Sub- contractor If sub-contracted (what %) ………. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. FISCAL DATA KES | a. AMOUNT OF BASIC CONTRACT |  |  |  |  | b. TOTAL AMOUNT OF MODIFICATIONS |  |  |  |  | c. LIQUIDATED DAMAGES ASSESSED |  |  |  |  |  | d. NET AMOUNT PAID CONTRACTOR |  |  |  |  |  |  |
| 10. SIGNIFICANT DATES | a. DATE OF AWARD |  |  |  |  | b. ORIGINAL CONTRACT COMPLETION DATE |  |  |  |  | c. REVISED CONTRACT COMPLETION DATE |  |  |  |  |  | d. DATE WORK ACCEPTED |  |  |  |  |  |  |
| PART II – PERFORMANCE EVALUATION OF CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. OVERALL RATING OUTSTANDING ABOVE AVERAGE SATISFACTORY MARGINAL UNSATISFACTORY (Explain in block 19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. EVALUATED BY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. ORGANIZATION [Name and Address (include ZIP Code)] US EMBASSY – FACILITIES MANAGEMENT US Embassy. Nairobi |  |  |  |  |  |  |  |  |  |  |  |  | b. TELEPHONE NUMBER (include Area Code) |  |  |  |  |  |  |  |  |  |  |
| c. NAME AND TITLE |  |  |  |  |  |  |  |  | d. SIGNATURE |  |  |  |  |  |  |  |  |  |  | e. DATE |  |  |  |
| 13. EVALUATION REVIEWED BY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. ORGANIZATION [Name and Address (include ZIP Code)] US EMBASSY – FACILITIES MANAGEMENT US Embassy. Nairobi |  |  |  |  |  |  |  |  |  |  |  |  | b. TELEPHONE NUMBER (include Area +254 020 3636442 |  |  |  |  |  |  |  |  |  |  |
| c. NAME AND TITLE |  |  |  |  |  |  |  |  | d. SIGNATURE |  |  |  |  |  | e. DATE |  |  |  |  |  |  |  |  |
| PART III – EVALUATION OF PERFORMANCE ELEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N/A = NOT APPLICABLE O = OUTSTANDING A = ABOVE AVERAGE S = SATISFACTORY M = MARGINAL U = UNSATISFACTORY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. QUALITY CONTROL |  | N/A | O | A | S |  | M | U |  | 15. EFFECTIVENESS OF MANAGEMENT |  |  |  |  | N/A |  |  | O | A |  | S | M | U |
| a. Quality of Workmanship |  |  |  |  |  |  |  |  |  | a. Cooperation & Responsiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b. Adequacy of CQC Plan |  |  |  |  |  |  |  |  |  | b. Management of Resources/Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. CQC Implementation Plan |  |  |  |  |  |  |  |  |  | c. Coordination & Control of Subs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Quality of QC Documentation |  |  |  |  |  |  |  |  |  | d. Adequacy of Site Clean-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Storage of Materials |  |  |  |  |  |  |  |  |  | e. Effectiveness of Job-Site Supervision |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Adequacy of Materials |  |  |  |  |  |  |  |  |  | f. Compliance w/Laws & Regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| g. Adequacy of Submittals |  |  |  |  |  |  |  |  |  | g. Professional Conduct |  |  |  |  |  |  |  |  |  |  |  |  |  |
| h. Storage of Testing |  |  |  |  |  |  |  |  |  | h. Review/Resolution of Subcontractors Issues |  |  |  |  |  |  |  |  |  |  |  |  |  |
| i. Storage of As-Builts |  |  |  |  |  |  |  |  |  | i. Implementation of Subcontracting Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| j. Use of Specified Materials |  |  |  |  |  |  |  |  |  | 17. COMPLAINACE WITH LABOR STANDARDS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| k. Identification/Correction of Deficient Work in a Timely Manner |  |  |  |  |  |  |  |  |  | a. Correction of Noted Deficiencies |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. TIMELY PERFORMANCE |  |  |  |  |  |  |  |  |  | b. Payrolls Properly Completed & Submitted |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. Adequacy of Initial Progress Schedule |  |  |  |  |  |  |  |  |  | c. Compliance w/Labor Laws and Regulations with Specify Attention to the Davis-Bacon Act and EEO Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b. Adherence to Approved Schedule |  |  |  |  |  |  |  |  |  | 18. COMPLIANCE WITH SAFETY STANDARDS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c. Resolution of Delays |  |  |  |  |  |  |  |  |  | a. Adequacy of Safety Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d. Submission of required Documentation |  |  |  |  |  |  |  |  |  | b. Implementation of Safety Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| e. Completion of Punchlist Items |  |  |  |  |  |  |  |  |  | c. Correction of Noted Deficiencies |  |  |  |  |  |  |  |  |  |  |  |  |  |
| f. Submission of Updated and Revised Progress Schedules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| j. Warranty Response |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |