SCOPE OF WORK

Central Asia Field Epidemiology Training Program:

Workshop on Epi Info, computer skills and surveillance evaluation,

Almaty, Kazakhstan, November 12 - December 7, 2018

Scope:

To provide logistic support for a four-week workshop on Epi Info, computer skills and surveillance evaluation organized by Central Asia Field Epidemiology Training Program (FETP) of the Centers for Disease Control and Prevention (CDC) in Almaty, Kazakhstan.

Background information:

The Central Asia FETP of the CDC office is a two-year residency in field epidemiology that trains local epidemiologists through service to the ministers of health in identification and response to disease threats. FETP promotes development of evidence-based public health in Central Asia. FETP is planning to conduct one four-week workshop designed to improve cohort -15 epidemiologists’ capacity to use EPI-INFO statistical software to enter, edit, and process questionnaire data from an investigation to product lists, frequencies, cross-tabulations, as well as to maintain high quality surveillance system.

Contractor tasks

During the period of this contract the contractor will work in cooperation and under the direction of the CDC/CAR FETP Manager to carry out the following tasks (please see the Schedule of dleiverables attached to this SOW):

- Invite by phone all 8 residents of FETP cohort -15 to Almaty to attend the four-week FETP workshop. The list of residents of the workshop will be provided to the contractor by the CDC/CAR FETP Manager as soon as the Contract is issued

- Arrange and pay for travel of 6 oblast residents to/from Almaty on the travel dates (travel days- November 11 and December 8, 2018).

  - The contractor needs to provide average cost estimates for travel in country to/from Almaty based on the following locations of participants:

    - Kostanay oblast – two participants

    - Easteren Kazakhstan- two participants

    - Atyrau- one participant

    - Western Kazakshstan- one participant

- Reimburse airport transportation for 6 oblast residents in Almaty on November 11 -December 8, 2018

- Arrange lodging in a proximity to training venue (November 11 - December 8, 2018)

- Provide  M&IE for 6 oblast residents

- Arrange and pay for a conference room for 8 residents and 2 facilitators in a three star hotel like Holiday Inn  for 50 days during the course and make sure that a conference package includes (screen; LCD projector + one laptop; Internet access, pointer; extension cords; flipchart, markers)

- Arrange and pay for duplication of course materials double sided, black and white pages:

  - 1,000 pages

- Paricipants kits (pen, pencil with eraser; 3 thick notebooks) for 8 residents

|  | Schedule of Deliverables and estimated budget |  |  |  |
| --- | --- | --- | --- | --- |
| # | Task | Deliverables dates | Cost | Total |
| 1 | Invite by phone all 8 residents of FETP Cohort 15 to Almaty to attend the four-week FETP workshop on Epi Info, computer skills and surveillance evaluation. The list of residents of the four-week workshop will be provide to the contractor by CDC/CAR FETP Manager as soon as the Contract is issued | 30-Sep-18 | n/a | n/a |
| 2 | Arrange and pay for travel of 6 oblast residents of the workshop to/from Almaty, November 11 - December 8, 2018 • Kostanay oblast – two participants • Easteren Kazakhstan- two participants • Atyrau- one participant • Western Kazakshstan- one participant | October 15, 2018- December 8, 2018 | ticket x 6 residents |  |
| 3 | Reimburse airport transportation for 6 oblast residents in Almaty on November 11 -December 8, 2018 | November 11 - December 8, 2018 | 6 residents x 7000KZT | 42,000.00 ₸ |
| 4 | Arrange lodging in a proximity to training venue (November 11 - December 8, 2018) | November 11 - December 8, 2018 | 6 residents x 28 days |  |
| 5 | Provide M&IE for 6 oblast residents | November 11 - December 8, 2018 | 6 residents x 7000KZT x 28 days | 1,176,000.00 ₸ |
| 6 | Arrange and pay for conference room for 8 residents and 2 facilitators in the three star hotel like Holiday Inn that includes conference package (screen; LCD projector +one laptop; Internet access, pointer; extension cords; flipchart, markers) | November 12 - December 7, 2018 | 10 participants x 20 days |  |
| 7 | Arrange and pay for duplication of Course materials 1,000 pages double sided, black and white) | November 12 - December 7, 2018 | 1,000 pages x 8 residents |  |
| 8 | Arrange participants' kits (pen, pencil with eraser, 3 thick notebooks) | November 12 - December 7, 2018 | 8 residents |  |
|  |  |  | TOTAL | 1,218,000.00 ₸ |

The U.S. Government shall provide

- List of Course residents

- Materials for duplication

Contract End Items

Satisfactory completion of the Contractor’s tasks: based on detailed financial report submitted to CDC/CAR upon completion of service (all payments to appropriate vendors should be done in time).

Period of Performance

September 30 - December 30, 2018

Estimated Contractors Fees & Expenses

Schedule of deliverables and independent government cost estimate follows.